## iNia-Scorecard
Account | Health Port | Project |  | PDM
Client Owner | Baskar | Delivery Owner |  | John
Q1 - 2015 - Week1
KPA |  |  |  | Score
Project Tracking |  |  |  | 40
Time Tracking |  |  |  | 100
Overall |  |  |  | 70
KRA | KPA | Goal | Unit | Descriptions | Accountability | Ownership | Earned Value (EV) | Weight | Target | Relative Performance | Absolute Performance
Planning | Planning against capacity | 20 | % | Tasks added to a Sprint and it's estimation should match with the team capacity | DO | CO | 0 | 0.2 | 100% | 0 | 0
| Un Managed Task | 5 | % | Unmanaged task (A task without due dates) 1. Is due date present for a task for which the status is not New, Suspend, Carried or Hold | DO | CO | 100 | 0.2 | 100% | 100 | 20
Monitor | Over due task | 5 | % | Overdue task (A task is considered as overdue when it is not completed on the due date) 1. Tasks closed on the specific due date. 2. Status set as resolved if closed is subject to client confirmation 3. Closed date should be within 2 working days from due date.Tickets to be associted with target versions 4. If overdue, status to be changed as Suspend/Hold marked with specific reason mentioned in the ticket | DO | CO | 100 | 0.2 | 100% | 100 | 20
Workflow adherence | Impact analysis | 5 | % | Impact analysis should be captured for all the applicable tickets in iNia and their respective comments to be added in the relevant custom fields | DO | CO | 0 | 0.1 | 100% | 0 | 0
| Unit test | 5 | % | Unit test results should be captured for all the tickets in iNia and their respective comments to be added in the relevant custom fields | DO | CO | 0 | 0.1 | 100% | 0 | 0
| Code review | 5 | % | Code review comments should be captured for all the applicable tickets in iNia and their respective comments to be added in the relevant custom fields | DO | CO | 0 | 0.1 | 100% | 0 | 0
Closure of sprints | Previous sprint items in open state | 5 | % | 1.Previous sprint items to be closed and if open, reason should be specified in the tickets and status to be marked as suspend, carried or hold | DO | CO | 100% | 0.1 | 100% | 100% | 0.1
Total Score | [7 empty] | 1 |  |  | 40
Time log | Time log by contributors,POD Owner and Product Owner | 100 | % | 1.All the contributors, POD owner and Product Owner (remote& Local) should log their efforts including the PTO | DO | CO | 100% | 0.4 | 100% | 100% | 40%
| Time log by DO | 100 | % | Respective DO should log their efforts Separately inside each projects | CO | NA | 100% | 0.2 | 100% | 100% | 20%
| Approval | 100 | % | L1 and L2 approval for team members time sheet | DO | CO | 100% | 0.4 | 100% | 100% | 40%
Total Score | [7 empty] | 1 |  |  | 100

## DataSheet
Tracker | All Tracker | Meeting | Support
Total | 48 | 8 | 0
Planning | Resource Capacity | Capacity (hrs) | Estimated
| 5.5 | 440 | 445.5
Variance |  |  | 1.2346
0
UnMangable | Count | Variance
| 0 | 0 | 100
OverDue | Count | Variance
| 0 | 100 | 100
Workflow | Count | Variance
Impact Analysis | 0 | 100 | 0
Unit Testing | 0 | 100 | 0
Code Review | 0 | 100 | 0

## Data
65513 | HealthPort - PDM | Task | Story #63670: PDM-316 Rollback Scripts | Closed | Minor Impact | Roll back script creation | sasikumar Sakthivel | sasikumar Sakthivel | 2015-04-01 12:41 | PDM_Q1_S6 [18-MAR-2015 till 31-MAR-2015] | 2015-03-31 | 2015-03-31 | 6 | 6 | 100 | 2015-04-01 12:40 | 2015-04-01 12:41 | 2015-03-31 | 2015-03-31 |  |  | 0
65410 | HealthPort - PDM | Testing | Story #63670: PDM-316 Rollback Scripts | Closed | Minor Impact | Test Execution | Bharath Veerappan | Bharath Veerappan | 2015-04-01 01:50 | PDM_Q1_S6 [18-MAR-2015 till 31-MAR-2015] | 2015-03-31 | 2015-03-31 | 4 | 4 | 100 | 2015-04-01 01:47 | 2015-04-01 01:50 | 2015-03-31 | 2015-03-31 |  |  | 0
65407 | HealthPort - PDM | Testing | Story #63654: PDM-253 Exception report on Salesforce Data Load | Closed | Minor Impact | Test Execution | Bharath Veerappan | Bharath Veerappan | 2015-03-31 22:13 | PDM_Q1_S6 [18-MAR-2015 till 31-MAR-2015] | 2015-03-31 | 2015-03-31 | 1 | 1 | 100 | 2015-03-31 22:11 | 2015-03-31 22:13 | 2015-03-31 | 2015-03-31 |  |  | 0
65210 | HealthPort - PDM | Task | Story #63671: PDM-317 Integrate server testcase with jenkins | Closed | Minor Impact | Test case creation for server code | sasikumar Sakthivel | Sriprem Ramdoss | 2015-04-01 12:43 | PDM_Q1_S6 [18-MAR-2015 till 31-MAR-2015] | 2015-03-30 | 2015-03-31 | 16 | 14.7 | 100 | 2015-03-31 00:50 | 2015-04-01 12:43 | 2015-03-30 | 2015-03-31 |  |  | 0
65209 | HealthPort - PDM | Task | Story #63654: PDM-253 Exception report on Salesforce Data Load | Closed | Minor Impact | Generating excel files for dedup & cleansing exceptions | sasikumar Sakthivel | sasikumar Sakthivel | 2015-04-01 12:39 | PDM_Q1_S6 [18-MAR-2015 till 31-MAR-2015] | 2015-03-30 | 2015-03-31 | 16 | 9 | 100 | 2015-03-31 00:43 | 2015-04-01 12:39 | 2015-03-30 | 2015-03-31 |  |  | 0
65208 | HealthPort - PDM | Task | Story #63673: PDM-312 PDM Optimization | Closed | Minor Impact | Angularjs UI modularity clean up | sasikumar Sakthivel | Shah Mohamed Nattar Shah | 2015-04-01 12:43 | PDM_Q1_S6 [18-MAR-2015 till 31-MAR-2015] | 2015-03-18 | 2015-03-31 | 7 | 0 | 100 | 2015-03-30 22:50 | 2015-04-01 12:43 | 2015-03-18 | 2015-03-31 |  |  | 0
64987 | HealthPort - PDM | Testing | Testing #64147: Q1-S6 Smoke Testing | Closed | Minor Impact | Pdm -103 Purge data and file | Suruthi Gopinathan | HP-PDM | 2015-03-30 17:16 | PDM_Q1_S6 [18-MAR-2015 till 31-MAR-2015] | 2015-03-27 | 2015-03-31 | 6 | 6 | 100 | 2015-03-30 12:12 | 2015-03-30 17:16 | 2015-03-27 | 2015-03-30 |  |  | 0
64951 | HealthPort - PDM | Task | Story #63659: PDM-103 Purge Data and File | Closed | Minor Impact | Development & testing | sasikumar Sakthivel | sasikumar Sakthivel | 2015-03-29 20:03 | PDM_Q1_S6 [18-MAR-2015 till 31-MAR-2015] | 2015-03-25 | 2015-03-27 | 20 | 21 | 100 | 2015-03-29 19:47 | 2015-03-29 20:02 | 2015-03-25 | 2015-03-27 |  |  | 0
64950 | HealthPort - PDM | Bug | Story #63657: PDM-251 Retry matching | Closed | Minor Impact | Empty block with todo statement in UI code | sasikumar Sakthivel | sasikumar Sakthivel | 2015-03-29 19:41 | PDM_Q1_S6 [18-MAR-2015 till 31-MAR-2015] | 2015-03-25 | 2015-03-25 | 2 | 2 | 100 | 2015-03-29 19:40 | 2015-03-29 19:41 | 2015-03-25 | 2015-03-25 |  | Removed the empty block along with the todo statement | 0
64914 | HealthPort - PDM | Task |  | Closed | Minor Impact | Asynchronous callbacks in Angular JS | Sriprem Ramdoss | Sriprem Ramdoss | 2015-03-30 22:39 | PDM_Q1_S6 [18-MAR-2015 till 31-MAR-2015] | 2015-03-27 | 2015-03-31 | 7.5 | 7.25 | 100 | 2015-03-27 19:25 | 2015-03-30 22:39 | 2015-03-27 | 2015-03-27 |  |  | 0
64869 | HealthPort - PDM | Task | Story #63654: PDM-253 Exception report on Salesforce Data Load | Closed | Minor Impact | Implement java mail services | Saravana Pandian Bose | Saravana Pandian Bose | 2015-03-31 22:35 | PDM_Q1_S6 [18-MAR-2015 till 31-MAR-2015] | 2015-03-27 | 2015-03-31 | 16 | 16 | 100 | 2015-03-27 17:43 | 2015-03-31 22:35 | 2015-03-27 | 2015-03-31 | Test the all scenario of loading the date using auto delta load. |  | 0
64791 | HealthPort - PDM | Testing |  | Closed | Minor | Validation of the Address1 and Address2 Match process | Suruthi Gopinathan | Suruthi Gopinathan | 2015-03-30 17:17 | PDM_Q1_S6 [18-MAR-2015 till 31-MAR-2015] | 2015-03-26 | 2015-03-27 | 8 | 8 | 100 | 2015-03-27 11:36 | 2015-03-30 17:17 | 2015-03-26 | 2015-03-28 |  |  | 0
64790 | HealthPort - PDM | Story |  | Closed | Minor | PDM-250 Automate the Delta data load | Suruthi Gopinathan | Suruthi Gopinathan | 2015-04-01 11:08 | PDM_Q1_S6 [18-MAR-2015 till 31-MAR-2015] | 2015-03-26 | 2015-03-27 | 10 | 10 | 100 | 2015-03-27 11:32 | 2015-04-01 11:08 | 2015-03-26 | 2015-03-31 |  |  | 0
64737 | HealthPort - PDM | Testing | Story #63660: PDM-250 Automate the Detla data load to HealthPort Provider Pool | Closed | Minor Impact | Test Execution | Bharath Veerappan | Bharath Veerappan | 2015-03-27 22:50 | PDM_Q1_S6 [18-MAR-2015 till 31-MAR-2015] | 2015-03-26 | 2015-03-31 | 7 | 7 | 100 | 2015-03-26 23:47 | 2015-03-27 22:50 | 2015-03-26 | 2015-03-27 |  |  | 0
64736 | HealthPort - PDM | Testing | Story #63660: PDM-250 Automate the Detla data load to HealthPort Provider Pool | Closed | Minor Impact | Test Data Preparation | Bharath Veerappan | Bharath Veerappan | 2015-03-26 23:52 | PDM_Q1_S6 [18-MAR-2015 till 31-MAR-2015] | 2015-03-26 | 2015-03-31 | 6 | 6 | 100 | 2015-03-26 23:47 | 2015-03-26 23:52 | 2015-03-26 | 2015-03-26 |  |  | 0
64735 | HealthPort - PDM | Story | Story #63660: PDM-250 Automate the Detla data load to HealthPort Provider Pool | Closed | Minor | Test Case Creation | Bharath Veerappan | Suruthi Gopinathan | 2015-04-01 13:19 | PDM_Q1_S6 [18-MAR-2015 till 31-MAR-2015] | 2015-03-26 | 2015-03-30 | 5 | 5 | 100 | 2015-03-26 23:46 | 2015-03-30 22:33 | 2015-03-30 | 2015-03-30 |  |  | 0
64608 | HealthPort - PDM | Testing |  | Closed | Minor | Match process for Address1 & Address 2 | Suruthi Gopinathan | Suruthi Gopinathan | 2015-03-30 17:28 | PDM_Q1_S6 [18-MAR-2015 till 31-MAR-2015] | 2015-03-25 | 2015-03-26 | 6 | 6 | 100 | 2015-03-26 11:28 | 2015-03-30 17:28 | 2015-03-25 | 2015-03-30 |  |  | 0
64501 | HealthPort - PDM | Testing | Story #63657: PDM-251 Retry matching | Closed | Minor Impact | Test Case Creation & Test Execution | Bharath Veerappan | Bharath Veerappan | 2015-03-26 12:25 | PDM_Q1_S6 [18-MAR-2015 till 31-MAR-2015] | 2015-03-23 | 2015-03-25 | 10 | 10 | 100 | 2015-03-25 13:24 | 2015-03-26 12:25 | 2015-03-24 | 2015-03-24 |  |  | 0
64471 | HealthPort - PDM | Bug | Story #63657: PDM-251 Retry matching | Closed | Minor Impact | PDM-330 Retry Button is in enabled status after click | sasikumar Sakthivel | sasikumar Sakthivel | 2015-03-25 11:20 | PDM_Q1_S6 [18-MAR-2015 till 31-MAR-2015] | 2015-03-24 | 2015-03-24 | 1 | 1 | 100 | 2015-03-25 11:19 | 2015-03-25 11:20 | 2015-03-24 | 2015-03-24 |  |  | 0
64469 | HealthPort - PDM | Testing |  | Closed | Minor Impact | PDM-251 Retry Matching | Suruthi Gopinathan | Suruthi Gopinathan | 2015-03-26 11:11 | PDM_Q1_S6 [18-MAR-2015 till 31-MAR-2015] | 2015-03-24 | 2015-03-26 | 8 | 8 | 100 | 2015-03-25 11:16 | 2015-03-26 11:11 | 2015-03-24 | 2015-03-25 |  |  | 0
64468 | HealthPort - PDM | Task | Story #63657: PDM-251 Retry matching | Closed | Minor Impact | Unit Testing | sasikumar Sakthivel | sasikumar Sakthivel | 2015-03-25 11:17 | PDM_Q1_S6 [18-MAR-2015 till 31-MAR-2015] | 2015-03-24 | 2015-03-24 | 2 | 2 | 100 | 2015-03-25 11:15 | 2015-03-25 11:17 | 2015-03-24 | 2015-03-24 |  | Done testing as per the acceptance criteria. No issue found. Will release it to QA | 0
64458 | HealthPort - PDM | Code Review | Story #63657: PDM-251 Retry matching | Closed | Minor Impact | Code Review | sasikumar Sakthivel | Saravana Pandian Bose | 2015-03-26 12:32 | PDM_Q1_S6 [18-MAR-2015 till 31-MAR-2015] | 2015-03-24 | 2015-03-24 | 1 | 1 | 100 | 2015-03-25 11:07 | 2015-03-26 12:26 | 2015-03-25 | 2015-03-25 |  | Code reviewed and review comments incorporated. | 0
64456 | HealthPort - PDM | Defect | Story #63657: PDM-251 Retry matching | Closed | Minor Impact | Expose service for the retry matching | sasikumar Sakthivel | sasikumar Sakthivel | 2015-03-25 22:03 | PDM_Q1_S6 [18-MAR-2015 till 31-MAR-2015] | 2015-03-23 | 2015-03-24 | 16 | 16 | 100 | 2015-03-25 11:04 | 2015-03-25 11:06 |  |  |  |  | 0
64309 | HealthPort - PDM | Task |  | Closed | Minor Impact | File details screen pagination as per style guide | Sriprem Ramdoss | Sriprem Ramdoss | 2015-03-30 11:06 | PDM_Q1_S6 [18-MAR-2015 till 31-MAR-2015] | 2015-03-24 | 2015-03-26 | 18 | 20.35 | 100 | 2015-03-24 20:07 | 2015-03-30 11:06 | 2015-03-24 | 2015-03-26 |  |  | 0
64147 | HealthPort - PDM | Testing |  | Closed | Minor Impact | Q1-S6 Smoke Testing | Bharath Veerappan | HP-PDM | 2015-03-31 22:05 | PDM_Q1_S6 [18-MAR-2015 till 31-MAR-2015] | 2015-03-27 | 2015-03-31 | 15 | 15 | 100 | 2015-03-24 10:48 | 2015-03-31 22:05 | 2015-03-18 | 2015-03-31 |  |  | 0
64146 | HealthPort - PDM | Testing |  | Closed | Minor Impact | Q1-S6 Regression Testing | Bharath Veerappan | HP-PDM | 2015-03-30 17:38 | PDM_Q1_S6 [18-MAR-2015 till 31-MAR-2015] | 2015-03-18 | 2015-03-31 | 10 | 10 | 100 | 2015-03-24 10:47 | 2015-03-30 17:38 | 2015-03-18 | 2015-03-30 |  |  | 0
64144 | HealthPort - PDM | Testing |  | Closed | Minor Impact | Q1-S6 Sanity Testing | Bharath Veerappan | HP-PDM | 2015-03-31 22:01 | PDM_Q1_S6 [18-MAR-2015 till 31-MAR-2015] | 2015-03-18 | 2015-03-31 | 4 | 4 | 100 | 2015-03-24 10:45 | 2015-03-31 22:01 | 2015-03-18 | 2015-03-31 |  |  | 0
64142 | HealthPort - PDM | Story | Story #63654: PDM-253 Exception report on Salesforce Data Load | Closed | Minor Impact | Development | Krishnamoorthy Ramasamy | Krishnamoorthy Ramasamy | 2015-03-30 11:47 | PDM_Q1_S6 [18-MAR-2015 till 31-MAR-2015] | 2015-03-19 | 2015-03-24 | 40 | 21 | 0 | 2015-03-24 10:43 | 2015-03-30 11:47 | 2015-03-19 |  |  |  | 0
64139 | HealthPort - PDM | Task | Story #63654: PDM-253 Exception report on Salesforce Data Load | Closed | Minor Impact | Design | Krishnamoorthy Ramasamy | Krishnamoorthy Ramasamy | 2015-03-24 10:42 | PDM_Q1_S6 [18-MAR-2015 till 31-MAR-2015] | 2015-03-18 | 2015-03-18 | 10 | 11 | 100 | 2015-03-24 10:41 | 2015-03-24 10:42 | 2015-03-18 | 2015-03-19 |  |  | 0
64000 | HealthPort - PDM | Story | Story #63654: PDM-253 Exception report on Salesforce Data Load | Closed | Minor Impact | Testcase preparation | Suruthi Gopinathan | Suruthi Gopinathan | 2015-03-24 11:37 | PDM_Q1_S6 [18-MAR-2015 till 31-MAR-2015] | 2015-03-20 | 2015-03-23 | 8 | 8 | 100 | 2015-03-23 11:45 | 2015-03-24 11:37 | 2015-03-20 | 2015-03-23 |  |  | 0
63879 | HealthPort - PDM | Task |  | Closed | Minor Impact | Pagination as per the style guide document | Sriprem Ramdoss | Sriprem Ramdoss | 2015-03-24 14:13 | PDM_Q1_S6 [18-MAR-2015 till 31-MAR-2015] | 2015-03-18 | 2015-03-20 | 20 | 19.75 | 100 | 2015-03-20 12:47 | 2015-03-24 14:13 | 2015-03-18 | 2015-03-20 |  |  | 0
63878 | HealthPort - PDM | Testing | Task #63870: Patch for PDP-1345 | Closed | Minor Impact | Testing on new Patch | sasikumar Sakthivel | sasikumar Sakthivel | 2015-03-23 12:35 | PDM_Q1_S6 [18-MAR-2015 till 31-MAR-2015] | 2015-03-20 | 2015-03-20 | 5 | 5 | 100 | 2015-03-20 12:43 | 2015-03-23 12:35 | 2015-03-20 | 2015-03-23 |  |  | 0
63874 | HealthPort - PDM | Task | Task #63870: Patch for PDP-1345 | Closed | Minor Impact | Creating a PRMATCH schema & updating scripts | sasikumar Sakthivel | sasikumar Sakthivel | 2015-03-20 12:38 | PDM_Q1_S6 [18-MAR-2015 till 31-MAR-2015] | 2015-03-19 | 2015-03-19 | 2 | 4 | 100 | 2015-03-20 12:38 | 2015-03-20 12:38 | 2015-03-19 | 2015-03-19 |  |  | 0
63870 | HealthPort - PDM | Task |  | Closed | Minor Impact | Patch for PDP-1345 | sasikumar Sakthivel | HP-PDM | 2015-03-23 12:36 | PDM_Q1_S6 [18-MAR-2015 till 31-MAR-2015] | 2015-03-19 | 2015-03-20 |  | 0 | 100 | 2015-03-20 12:36 | 2015-03-23 12:36 | 2015-03-19 | 2015-03-23 |  |  | 0
63866 | HealthPort - PDM | Meetings |  | Closed | Minor Impact | PDM - Process Flow discussion | sasikumar Sakthivel | HP-PDM | 2015-03-20 12:42 | PDM_Q1_S6 [18-MAR-2015 till 31-MAR-2015] | 2015-03-19 | 2015-03-19 | 6 | 3 | 100 | 2015-03-20 12:25 | 2015-03-20 12:42 | 2015-03-19 |  |  |  | 0
63865 | HealthPort - PDM | Code Review | Story #63655: PDM-309 The user is not able to see old file summary details which was uploaded before the summary(cl_provider_file_summary) table was created | Closed | Minor Impact | Code Review | sasikumar Sakthivel | Saravana Pandian Bose | 2015-03-20 12:34 | PDM_Q1_S6 [18-MAR-2015 till 31-MAR-2015] | 2015-03-19 | 2015-03-19 | 1 | 1 | 100 | 2015-03-20 12:23 | 2015-03-20 12:34 | 2015-03-19 | 2015-03-19 |  | Script verified. | 0
63864 | HealthPort - PDM | Unit Testing | Story #63655: PDM-309 The user is not able to see old file summary details which was uploaded before the summary(cl_provider_file_summary) table was created | Closed | Minor Impact | Unit Testing | sasikumar Sakthivel | sasikumar Sakthivel | 2015-03-20 12:23 | PDM_Q1_S6 [18-MAR-2015 till 31-MAR-2015] | 2015-03-18 | 2015-03-19 | 4 | 4 | 100 | 2015-03-20 12:21 | 2015-03-20 12:23 | 2015-03-18 | 2015-03-19 | 1. Cleaned the data from the cl_provider_file_summary table. 2. Ran the one time scripts 2. It pulled all the data again to the table |  | 0
63863 | HealthPort - PDM | Task | Story #63655: PDM-309 The user is not able to see old file summary details which was uploaded before the summary(cl_provider_file_summary) table was created | Closed | Minor Impact | Creating the one time script | sasikumar Sakthivel | sasikumar Sakthivel | 2015-03-20 13:11 | PDM_Q1_S6 [18-MAR-2015 till 31-MAR-2015] | 2015-03-18 | 2015-03-18 | 6 | 6 | 100 | 2015-03-20 12:17 | 2015-03-20 12:20 | 2015-03-18 | 2015-03-18 |  |  | 0
63744 | HealthPort - PDM | Task | Story #63660: PDM-250 Automate the Detla data load to HealthPort Provider Pool | Closed | Minor Impact | Development | Saravana Pandian Bose | Saravana Pandian Bose | 2015-03-27 | PDM_Q1_S6 [18-MAR-2015 till 31-MAR-2015] | 2015-03-19 | 2015-03-27 | 30 | 39 | 100 | 2015-03-19 18:54 | 2015-03-27 | 2015-03-19 | 2015-03-26 | Tested with different senarios with modified date. |  | 0
63690 | HealthPort - PDM | Testing |  | Closed | Minor Impact | Testcase preparation | Suruthi Gopinathan | Suruthi Gopinathan | 2015-03-24 11:51 | PDM_Q1_S6 [18-MAR-2015 till 31-MAR-2015] | 2015-03-18 | 2015-03-23 | 8 | 8 | 100 | 2015-03-19 14:00 | 2015-03-24 11:51 | 2015-03-18 | 2015-03-23 |  |  | 0
63682 | HealthPort - PDM | Task | Story #63660: PDM-250 Automate the Detla data load to HealthPort Provider Pool | Closed | Minor Impact | Design | Saravana Pandian Bose | Saravana Pandian Bose | 2015-03-30 22:03 | PDM_Q1_S6 [18-MAR-2015 till 31-MAR-2015] | 2015-03-18 | 2015-03-19 | 8 | 8 | 100 | 2015-03-19 13:06 | 2015-03-20 12:31 | 2015-03-18 | 2015-03-19 |  |  | 0
63673 | HealthPort - PDM | Story |  | Closed | Minor Impact | PDM-312 PDM Optimization | Saravana Pandian Bose | HP-PDM | 2015-04-01 12:48 | PDM_Q1_S6 [18-MAR-2015 till 31-MAR-2015] | 2015-03-18 | 2015-03-31 |  | 7 | 100 | 2015-03-19 12:25 | 2015-04-01 12:47 | 2015-03-18 | 2015-03-31 |  |  | 0
63671 | HealthPort - PDM | Story |  | Closed | Minor Impact | PDM-317 Integrate server testcase with jenkins | Saravana Pandian Bose | HP-PDM | 2015-04-01 12:44 | PDM_Q1_S6 [18-MAR-2015 till 31-MAR-2015] | 2015-03-30 | 2015-03-31 | 0 | 0 | 100 | 2015-03-19 12:24 | 2015-04-01 12:44 | 2015-03-30 | 2015-03-31 |  |  | 0
63670 | HealthPort - PDM | Story |  | Closed | Minor Impact | PDM-316 Rollback Scripts | Saravana Pandian Bose | HP-PDM | 2015-04-01 12:49 | PDM_Q1_S6 [18-MAR-2015 till 31-MAR-2015] | 2015-03-31 | 2015-03-31 |  | 0 | 100 | 2015-03-19 12:23 | 2015-04-01 12:49 | 2015-03-31 | 2015-03-31 |  |  | 0
63660 | HealthPort - PDM | Story |  | Closed | Minor | PDM-250 Automate the Detla data load to HealthPort Provider Pool | Saravana Pandian Bose | HP-PDM | 2015-03-31 12:09 | PDM_Q1_S6 [18-MAR-2015 till 31-MAR-2015] | 2015-03-18 | 2015-03-31 |  | 1 | 100 | 2015-03-19 12:14 | 2015-03-30 22:34 | 2015-03-18 | 2015-03-30 |  |  | 0
63659 | HealthPort - PDM | Story |  | Closed | Minor Impact | PDM-103 Purge Data and File | Saravana Pandian Bose | HP-PDM | 2015-03-29 21:40 | PDM_Q1_S6 [18-MAR-2015 till 31-MAR-2015] | 2015-03-25 | 2015-03-27 |  | 16 | 100 | 2015-03-19 12:13 | 2015-03-29 21:40 | 2015-03-25 | 2015-03-27 | 1. Upload file purging - Working as expected 2. Data level purging - Working as expected 3. Download file purging - Working as expected | Code review is done by onsite. No comments received. | 0
63657 | HealthPort - PDM | Story |  | Closed | Minor Impact | PDM-251 Retry matching | Saravana Pandian Bose | HP-PDM | 2015-03-29 19:42 | PDM_Q1_S6 [18-MAR-2015 till 31-MAR-2015] | 2015-03-23 | 2015-03-25 |  | 0 | 100 | 2015-03-19 12:11 | 2015-03-29 19:42 | 2015-03-23 | 2015-03-25 |  |  | 0
63655 | HealthPort - PDM | Story |  | Closed | Minor Impact | PDM-309 The user is not able to see old file summary details which was uploaded before the summary(cl_provider_file_summary) table was created | Saravana Pandian Bose | HP-PDM | 2015-03-20 13:10 | PDM_Q1_S6 [18-MAR-2015 till 31-MAR-2015] | 2015-03-18 | 2015-03-19 |  | 0 | 100 | 2015-03-19 12:10 | 2015-03-20 13:10 | 2015-03-18 | 2015-03-19 |  |  | 0
63654 | HealthPort - PDM | Story |  | Closed | Minor Impact | PDM-253 Exception report on Salesforce Data Load | Saravana Pandian Bose | HP-PDM | 2015-04-01 12:39 | PDM_Q1_S6 [18-MAR-2015 till 31-MAR-2015] | 2015-03-18 | 2015-03-31 |  | 8 | 100 | 2015-03-19 12:10 | 2015-04-01 12:39 | 2015-03-18 |  |  |  | 0
63652 | HealthPort - PDM | Meetings | Meetings #63646: Sprint Ceremonies | Closed | Minor Impact | Sprint Planning | sasikumar Sakthivel | HP-PDM | 2015-03-30 21:54 | PDM_Q1_S6 [18-MAR-2015 till 31-MAR-2015] | 2015-03-18 | 2015-03-31 | 6 | 3.5 | 100 | 2015-03-19 12:08 | 2015-03-30 21:54 | 2015-03-18 |  |  |  | 0
63651 | HealthPort - PDM | Meetings | Meetings #63646: Sprint Ceremonies | Closed | Minor Impact | Daily Stand up - Offshore | sasikumar Sakthivel | HP-PDM | 2015-04-01 12:48 | PDM_Q1_S6 [18-MAR-2015 till 31-MAR-2015] | 2015-03-18 | 2015-03-31 | 25 | 30.95 | 100 | 2015-03-19 12:08 | 2015-04-01 12:48 | 2015-03-18 |  |  |  | 0
63650 | HealthPort - PDM | Meetings | Meetings #63646: Sprint Ceremonies | Closed | Minor Impact | Stand up - Onsite Call | sasikumar Sakthivel | HP-PDM | 2015-04-01 12:48 | PDM_Q1_S6 [18-MAR-2015 till 31-MAR-2015] | 2015-03-18 | 2015-03-31 | 25 | 30.2 | 100 | 2015-03-19 12:08 | 2015-04-01 12:48 | 2015-03-18 |  |  |  | 0
63649 | HealthPort - PDM | Meetings | Meetings #63646: Sprint Ceremonies | Closed | Minor Impact | POD Owner meeting | sasikumar Sakthivel | sasikumar Sakthivel | 2015-04-01 12:48 | PDM_Q1_S6 [18-MAR-2015 till 31-MAR-2015] | 2015-03-18 | 2015-03-31 | 2.5 | 2.5 | 100 | 2015-03-19 12:08 | 2015-04-01 12:48 | 2015-03-18 |  |  |  | 0
63648 | HealthPort - PDM | Meetings | Meetings #63646: Sprint Ceremonies | Closed | Minor Impact | Sprint Grooming | sasikumar Sakthivel | HP-PDM | 2015-03-30 21:51 | PDM_Q1_S6 [18-MAR-2015 till 31-MAR-2015] | 2015-03-18 | 2015-03-31 | 7 | 5 | 100 | 2015-03-19 12:08 | 2015-03-30 21:51 | 2015-03-18 |  |  |  | 0
63647 | HealthPort - PDM | Meetings | Meetings #63646: Sprint Ceremonies | Closed | Minor Impact | Sprint Retrospective | sasikumar Sakthivel | HP-PDM | 2015-04-02 13:24 | PDM_Q1_S6 [18-MAR-2015 till 31-MAR-2015] | 2015-03-18 | 2015-03-31 | 3.5 | 2.5 | 100 | 2015-03-19 12:07 | 2015-04-02 13:24 | 2015-04-01 |  |  |  | 0
63646 | HealthPort - PDM | Meetings |  | Closed | Minor Impact | Sprint Ceremonies | sasikumar Sakthivel | HP-PDM | 2015-04-02 13:25 | PDM_Q1_S6 [18-MAR-2015 till 31-MAR-2015] | 2015-03-18 | 2015-03-31 |  | 1 | 100 | 2015-03-19 12:07 | 2015-04-02 13:25 | 2015-03-18 |  |  |  | 0