## iNia-Scorecard
Account | Account Name | Project |  | Project Name
Client Owner | Client Owner Name | Delivery Owner |  | Delivery Owner Name
Q1 - 2015 - Week1
KPA |  |  |  | Score
Project Tracking |  |  |  | #DIV/0!
Time Tracking |  |  |  | 100
Overall |  |  |  | #DIV/0!
KRA | KPA | Goal | Unit | Descriptions | Accountability | Ownership | Earned Value (EV) | Weight | Target | Relative Performance | Absolute Performance
Planning | Planning against capacity | 20 | % | Tasks added to a Sprint and it's estimation should match with the team capacity | DO | CO | 100 | 0.2 | 100% | 100 | 20
| Un Managed Task | 5 | % | Unmanaged task (A task without due dates) 1. Is due date present for a task for which the status is not New, Suspend, Carried or Hold | DO | CO | 100 | 0.2 | 100% | 100 | 20
Monitor | Over due task | 5 | % | Overdue task (A task is considered as overdue when it is not completed on the due date) 1. Tasks closed on the specific due date. 2. Status set as resolved if closed is subject to client confirmation 3. Closed date should be within 2 working days from due date.Tickets to be associted with target versions 4. If overdue, status to be changed as Suspend/Hold marked with specific reason mentioned in the ticket | DO | CO | 100 | 0.1 | 100% | 100 | 10
Workflow adherence | Impact analysis | 5 | % | Impact analysis should be captured for all the applicable tickets in iNia and their respective comments to be added in the relevant custom fields | DO | CO | 0 | 0.1 | 100% | 0 | 0
| Unit test | 5 | % | Unit test results should be captured for all the tickets in iNia and their respective comments to be added in the relevant custom fields | DO | CO | #DIV/0! | 0.1 | 100% | #DIV/0! | #DIV/0!
| Code review | 5 | % | Code review comments should be captured for all the applicable tickets in iNia and their respective comments to be added in the relevant custom fields | DO | CO | #DIV/0! | 0.1 | 100% | #DIV/0! | #DIV/0!
PMO Observation | Follow best practices Ref: http://inia.objectfrontier.com/redmine/projects/redmine/wiki/INia_Best_practices | N/A | N/A | 1. Usage of Tracker (e.g. Bug should not be posted as Support tracker) 2. Review comments clarity 3. Naming conventions (e.g Sprint Name) 4. Tracking of previous sprint open items | DO | CO | 100% | 0.2 | 100% | 75 | 15
Total Score | [7 empty] | 1 |  |  | #DIV/0!
Time log | Time log by contributors,POD Owner and Product Owner | 100 | % | 1.All the contributors, POD owner and Product Owner (remote& Local) should log their efforts including the PTO | DO | CO | 100% | 0.4 | 100% | 100 | 40
| Time log by DO | 100 | % | Respective DO should log their efforts Separately inside each projects | CO | NA | 100% | 0.2 | 100% | 100 | 20
| Approval | 100 | % | L1 and L2 approval for team members time sheet | DO | CO | 100% | 0.4 | 100% | 100 | 40
Total Score | [7 empty] | 1 |  |  | 100

## DataSheet
Tracker | All Tracker | Meeting | Support | Story&Bug
Total | 35 | 14 | 18 | 0
Planning | Resource Capacity | Capacity (hrs) | Estimated
| 5.5 | 440 | 269.5
Variance |  |  | -63.2653
100
UnMangable | Count | Variance
| 0 | 0 | 100
OverDue | Count | Variance
| 0 | 100 | 100
Workflow | Count | Variance
Impact Analysis | 0 | #DIV/0! | 0
Unit Testing | 0 | #DIV/0! | #DIV/0!
Code Review | 0 | #DIV/0! | #DIV/0!

## Data
67308 | SMC | Support | Closed | Minor Impact | Automation scenario for HELP page in PCAP Configuration UI | Naga Natarajan | Vijayasaravanan Kannan | 2015-04-15 21:22 | Sprint G01 04/01/15 - 04/14/15 | 2015-04-14 | 2015-04-14 | 2 | 2.5 | 100 | 2015-04-15 12:58 | 2015-04-15 21:22 | Copied from #67307 | 2015-04-14 | 2015-04-14 |  | 0
67301 | SMC | Support | Closed | Minor Impact | iNia task verification | Naga Natarajan | Naga Natarajan | 2015-04-15 12:47 | Sprint G01 04/01/15 - 04/14/15 | 2015-04-13 | 2015-04-14 | 2 | 2 | 0 | 2015-04-15 12:44 | 2015-04-15 12:47 |  | 2015-04-13 |  |  | 0
67187 | SMC | Meetings | Closed | Minor Impact | Lancope - Sprint G02 Planning Meeting | Naga Natarajan | Lancope | 2015-04-15 21:22 | Sprint G01 04/01/15 - 04/14/15 | 2015-04-14 | 2015-04-14 | 4.5 | 1.75 | 0 | 2015-04-14 18:31 | 2015-04-15 21:22 | Copied from #67186 | 2015-04-14 |  |  | 0
67186 | SMC | Meetings | Closed | Minor Impact | Lancope - Sprint G02 Planning Meeting | Naga Natarajan | Naga Natarajan | 2015-04-15 12:47 | Sprint G01 04/01/15 - 04/14/15 | 2015-04-14 | 2015-04-14 | 1.5 | 1.5 | 0 | 2015-04-14 18:30 | 2015-04-15 12:47 | Copied from #67185, Copied to #67187 | 2015-04-14 |  |  | 0
67185 | SMC | Meetings | Closed | Minor Impact | Lancope - Sprint G02 Planning Meeting | Naga Natarajan | Ghazni Nattarshah | 2015-04-14 18:31 | Sprint G01 04/01/15 - 04/14/15 | 2015-04-14 | 2015-04-14 | 1.5 | 1.5 | 0 | 2015-04-14 18:29 | 2015-04-14 18:31 | Copied to #67186 | 2015-04-14 |  |  | 0
67157 | SMC | Support | Closed | Minor Impact | PTO | Naga Natarajan | Gayathri Sukumar | 2015-04-15 21:22 | Sprint G01 04/01/15 - 04/14/15 | 2015-04-14 | 2015-04-14 | 8 | 8 | 0 | 2015-04-14 13:17 | 2015-04-15 21:22 |  |  |  |  | 0
67139 | SMC | Code Review | Closed | Minor Impact | Code Review for US3964 - PCAP: Spike - Can we use Job Management for PCAP? | Naga Natarajan | Ghazni Nattarshah | 2015-04-15 21:22 | Sprint G01 04/01/15 - 04/14/15 | 2015-04-14 | 2015-04-14 | 2 | 1 | 0 | 2015-04-14 12:03 | 2015-04-15 21:22 |  | 2015-04-14 |  | 1. Model.js, Change the variable isRequireBuildQuery to just useSimpleFlowQuery 2. PCAPController: 84, set file length to content length 3. Use @Autowired to inject bean, instead of defining bean in jobContext.xml 4. Have the methods and important business logic commented. 5. Prefix the constant for field and value with KEY_ 6. Give empty line if a method or a scope that has more than two lines. | 0
67075 | SMC | Support | Closed | Minor Impact | Support Team for the current user story tasks | Naga Natarajan | Naga Natarajan | 2015-04-15 12:47 | Sprint G01 04/01/15 - 04/14/15 | 2015-04-07 | 2015-04-14 | 30 | 30.5 | 0 | 2015-04-13 20:46 | 2015-04-15 12:47 |  | 2015-04-07 |  |  | 0
66986 | SMC | Support | Closed | Minor Impact | Technical Support for the task US3566 - TA5138 - Dev: Write test case for adding PCAP appliance configuration | Naga Natarajan | Ghazni Nattarshah | 2015-04-14 14:13 | Sprint G01 04/01/15 - 04/14/15 | 2015-04-13 | 2015-04-13 | 0.5 | 1 | 0 | 2015-04-13 15:40 | 2015-04-14 14:13 |  | 2015-04-13 | 2015-04-13 |  | 0
66985 | SMC | Code Review | Closed | Minor Impact | Code Review for user story US3929 - PCAP: Arch - Create REST client framework for PCAP | Naga Natarajan | Lakshmi Prabha Nagarajan | 2015-04-14 14:31 | Sprint G01 04/01/15 - 04/14/15 | 2015-04-13 | 2015-04-13 | 1 | 2 | 100 | 2015-04-13 15:39 | 2015-04-14 14:31 |  | 2015-04-13 |  | Attached the txt file contains code review comments. Lakshmi Prabha : Implemented the review comments in the attachement. | 0
66944 | SMC | Support | Closed | Minor Impact | PTO | Naga Natarajan | Kaviyarasi Venkatachalam | 2015-04-13 14:54 | Sprint G01 04/01/15 - 04/14/15 | 2015-04-08 | 2015-04-08 | 8 | 8 | 0 | 2015-04-13 12:47 | 2015-04-13 14:54 |  | 2015-04-08 |  |  | 0
66697 | SMC | Support | Closed | Minor Impact | PTO | Naga Natarajan | Lakshmi Prabha Nagarajan | 2015-04-10 13:23 | Sprint G01 04/01/15 - 04/14/15 | 2015-04-08 | 2015-04-08 | 8 | 8 | 0 | 2015-04-10 12:28 | 2015-04-10 13:23 |  |  |  |  | 0
66576 | SMC | Meetings | Closed | Minor Impact | W3H Document Review with EO | Naga Natarajan | Ghazni Nattarshah | 2015-04-14 14:13 | Sprint G01 04/01/15 - 04/14/15 | 2015-04-09 | 2015-04-09 | 1 | 3 | 0 | 2015-04-09 15:22 | 2015-04-14 14:13 | Copied from #66575 | 2015-04-09 |  |  | 0
66575 | SMC | Meetings | Closed | Minor Impact | W3H Document Review with EO | Naga Natarajan | Naga Natarajan | 2015-04-09 15:27 | Sprint G01 04/01/15 - 04/14/15 | 2015-04-09 | 2015-04-09 | 1 | 1 | 0 | 2015-04-09 15:22 | 2015-04-09 15:27 | Copied from #66574, Copied to #66576 | 2015-04-09 |  |  | 0
66574 | SMC | Meetings | Closed | Minor Impact | W3H Document Review with EO | Naga Natarajan | Lancope | 2015-04-14 14:01 | Sprint G01 04/01/15 - 04/14/15 | 2015-04-09 | 2015-04-09 | 5 | 7.25 | 0 | 2015-04-09 15:18 | 2015-04-14 14:01 | Copied to #66575 | 2015-04-09 |  |  | 0
66214 | SMC | Support | Closed | Minor Impact | Metrics & audit document preparation for Lancope Surveillance Audit | Naga Natarajan | Naga Natarajan | 2015-04-10 11:45 | Sprint G01 04/01/15 - 04/14/15 | 2015-04-06 | 2015-04-06 | 4 | 3.5 | 0 | 2015-04-07 13:56 | 2015-04-10 11:45 |  | 2015-04-06 | 2015-04-06 | NA | 0
66213 | SMC | Meetings | Closed | Minor Impact | Surveillance Audit - Lancope | Naga Natarajan | Naga Natarajan | 2015-04-07 13:54 | Sprint G01 04/01/15 - 04/14/15 | 2015-04-06 | 2015-04-06 | 1.5 | 1.5 | 0 | 2015-04-07 13:53 | 2015-04-07 13:54 |  | 2015-04-06 |  |  | 0
66203 | SMC | Support | Closed | Minor Impact | Support team for the story US3566 - TA5127 - UI: Create UI to add PCAP appliance configuration | Naga Natarajan | Naga Natarajan | 2015-04-07 13:03 | Sprint G01 04/01/15 - 04/14/15 | 2015-04-06 | 2015-04-06 | 1 | 0.75 | 100 | 2015-04-07 12:47 | 2015-04-07 13:02 |  | 2015-04-06 | 2015-04-06 | NA | 0
66202 | SMC | Support | Closed | Minor Impact | Support team for the story US3566 - TA5134 - Dev: Update Service layer to expose save API method | Naga Natarajan | Naga Natarajan | 2015-04-07 13:03 | Sprint G01 04/01/15 - 04/14/15 | 2015-04-06 | 2015-04-06 | 1.5 | 1.5 | 100 | 2015-04-07 12:46 | 2015-04-07 13:03 |  | 2015-04-06 | 2015-04-06 | NA | 0
66032 | SMC | Support | Closed | Minor Impact | Estimation for REST Client Implementation | Naga Natarajan | Lakshmi Prabha Nagarajan | 2015-04-06 13:01 | Sprint G01 04/01/15 - 04/14/15 | 2015-04-02 | 2015-04-02 | 4 | 4 | 100 | 2015-04-06 12:57 | 2015-04-06 13:01 |  | 2015-04-02 |  |  | 0
66007 | SMC | Meetings | Closed | Minor Impact | Surveillance Audit Opening Meeting | Naga Natarajan | Naga Natarajan | 2015-04-06 11:17 | Sprint G01 04/01/15 - 04/14/15 | 2015-04-06 | 2015-04-06 | 0.5 | 0.5 | 0 | 2015-04-06 10:58 | 2015-04-06 11:17 |  | 2015-04-06 |  |  | 0
65840 | SMC | Support | Closed | Minor Impact | Creating Sprint G01 user story in iNia | Naga Natarajan | Naga Natarajan | 2015-04-06 11:27 | Sprint G01 04/01/15 - 04/14/15 | 2015-04-02 | 2015-04-02 | 1 | 1 | 0 | 2015-04-02 14:00 | 2015-04-06 11:27 |  | 2015-04-02 | 2015-04-02 |  | 0
65832 | SMC | Support | Closed | Minor Impact | PTO | Naga Natarajan | Arokia Justus Maria Nayagam | 2015-04-06 12:26 | Sprint G01 04/01/15 - 04/14/15 | 2015-04-02 | 2015-04-02 | 8 | 8 | 0 | 2015-04-02 13:45 | 2015-04-06 12:26 |  | 2015-04-02 | 2015-04-02 |  | 0
65831 | SMC | Support | Closed | Minor Impact | OFS Holiday | Naga Natarajan | Naga Natarajan | 2015-04-06 11:17 | Sprint G01 04/01/15 - 04/14/15 | 2015-04-03 | 2015-04-03 | 8 | 8 | 0 | 2015-04-02 13:44 | 2015-04-06 11:17 | Copied from #65830 | 2015-04-03 | 2015-04-03 |  | 0
65830 | SMC | Support | Closed | Minor Impact | OFS Holiday | Naga Natarajan | Lancope | 2015-04-07 13:40 | Sprint G01 04/01/15 - 04/14/15 | 2015-04-03 | 2015-04-03 | 48 | 40 | 0 | 2015-04-02 13:44 | 2015-04-07 13:40 | Copied to #65831 | 2015-04-03 | 2015-04-03 |  | 0
65828 | SMC | Support | Closed | Minor Impact | PTO | Naga Natarajan | Naga Natarajan | 2015-04-06 11:18 | Sprint G01 04/01/15 - 04/14/15 | 2015-04-02 | 2015-04-02 | 4 | 4 | 0 | 2015-04-02 13:43 | 2015-04-06 11:18 |  | 2015-04-02 | 2015-04-02 |  | 0
65807 | SMC | Analysis | Closed | Minor Impact | Analysing how to implement a REST Client layer in our server side code using Jersy Jackson library for REST | Naga Natarajan | Lakshmi Prabha Nagarajan | 2015-04-06 11:18 | Sprint G01 04/01/15 - 04/14/15 | 2015-04-01 | 2015-04-01 | 4 | 3.75 | 100 | 2015-04-02 13:05 | 2015-04-06 11:18 |  |  |  |  | 0
65789 | SMC | Support | Closed | Minor Impact | Create job to execute packet search | Naga Natarajan | Gayathri Sukumar | 2015-04-06 11:18 | Sprint G01 04/01/15 - 04/14/15 | 2015-04-01 | 2015-04-01 | 3 | 3.5 | 0 | 2015-04-02 12:15 | 2015-04-06 11:18 |  | 2015-04-01 | 2015-04-01 | NA | 0
65786 | SMC | Meetings | Closed | Minor Impact | Lancope SMC - G01 Sprint Planning Meeting | Naga Natarajan | Naga Natarajan | 2015-04-06 11:18 | Sprint G01 04/01/15 - 04/14/15 | 2015-04-01 | 2015-04-01 | 1.5 | 1.5 | 0 | 2015-04-02 12:11 | 2015-04-06 11:18 | Copied from #65785 | 2015-04-01 |  |  | 0
65785 | SMC | Meetings | Closed | Minor Impact | Lancope SMC - G01 Sprint Planning Meeting | Naga Natarajan | Lancope | 2015-04-06 11:27 | Sprint G01 04/01/15 - 04/14/15 | 2015-04-01 | 2015-04-01 | 9 | 6 | 0 | 2015-04-02 12:10 | 2015-04-06 11:27 | Copied to #65786 | 2015-04-01 |  |  | 0
65784 | SMC | Support | Closed | Minor Impact | iNia Cleanup for Audit | Naga Natarajan | Naga Natarajan | 2015-04-06 11:46 | Sprint G01 04/01/15 - 04/14/15 | 2015-04-01 | 2015-04-02 | 8 | 6.5 | 0 | 2015-04-02 12:08 | 2015-04-06 11:46 |  | 2015-04-01 |  |  | 0
65783 | SMC | Meetings | Closed | Minor Impact | Lancope - Daily Status Call with Onsite | Naga Natarajan | Naga Natarajan | 2015-04-15 12:47 | Sprint G01 04/01/15 - 04/14/15 | 2015-04-01 | 2015-04-15 | 10 | 12.5 | 0 | 2015-04-02 12:07 | 2015-04-15 12:47 | Copied from #65782 | 2015-04-01 |  |  | 0
65782 | SMC | Meetings | Closed | Minor Impact | Lancope - Daily Status Call with Onsite | Naga Natarajan | Lancope | 2015-04-15 21:22 | Sprint G01 04/01/15 - 04/14/15 | 2015-04-01 | 2015-04-15 | 60 | 40.75 | 0 | 2015-04-02 12:07 | 2015-04-15 21:22 | Copied to #65783 | 2015-04-01 |  |  | 0
65781 | SMC | Meetings | Closed | Minor Impact | Lancope - Daily Scrum Meeting | Naga Natarajan | Naga Natarajan | 2015-04-15 12:48 | Sprint G01 04/01/15 - 04/14/15 | 2015-04-02 | 2015-04-15 | 1.5 | 8 | 0 | 2015-04-02 12:06 | 2015-04-15 12:48 | Copied from #65780 | 2015-04-01 |  |  | 0
65780 | SMC | Meetings | Closed | Minor Impact | Lancope - Daily Scrum Meeting | Naga Natarajan | Lancope | 2015-04-15 21:22 | Sprint G01 04/01/15 - 04/14/15 | 2015-04-02 | 2015-04-15 | 15 | 8.25 | 0 | 2015-04-02 12:05 | 2015-04-15 21:22 | Copied to #65781 | 2015-04-01 |  |  | 0