## iNia-Scorecard
Account | Account Name | Project |  | Project Name
Client Owner | Client Owner Name | Delivery Owner |  | Delivery Owner Name
Q1 - 2015 - Week1
KPA |  |  |  | Score
Project Tracking |  |  |  | #DIV/0!
Time Tracking |  |  |  | 100
Overall |  |  |  | #DIV/0!
KRA | KPA | Goal | Unit | Descriptions | Accountability | Ownership | Earned Value (EV) | Weight | Target | Relative Performance | Absolute Performance
Planning | Planning against capacity | -20 | % | Tasks added to a Sprint and it's estimation should match with the team capacity | DO | CO | 0 | 0.2 | 100% | 0 | 0
| Un Managed Task | 5 | % | Unmanaged task (A task without due dates) 1. Is due date present for a task for which the status is not New, Suspend, Carried or Hold | DO | CO | 100 | 0.2 | 100% | 100 | 20
Monitor | Over due task | 5 | % | Overdue task (A task is considered as overdue when it is not completed on the due date) 1. Tasks closed on the specific due date. 2. Status set as resolved if closed is subject to client confirmation 3. Closed date should be within 2 working days from due date.Tickets to be associted with target versions 4. If overdue, status to be changed as Suspend/Hold marked with specific reason mentioned in the ticket | DO | CO | 100 | 0.1 | 100% | 100 | 10
Workflow adherence | Impact analysis | 5 | % | Impact analysis should be captured for all the applicable tickets in iNia and their respective comments to be added in the relevant custom fields | DO | CO | 0 | 0.1 | 100% | 0 | 0
| Unit test | 5 | % | Unit test results should be captured for all the tickets in iNia and their respective comments to be added in the relevant custom fields | DO | CO | #DIV/0! | 0.1 | 100% | #DIV/0! | #DIV/0!
| Code review | 5 | % | Code review comments should be captured for all the applicable tickets in iNia and their respective comments to be added in the relevant custom fields | DO | CO | #DIV/0! | 0.1 | 100% | #DIV/0! | #DIV/0!
PMO Observation | Follow best practices Ref: http://inia.objectfrontier.com/redmine/projects/redmine/wiki/INia_Best_practices | N/A | N/A | 1. Usage of Tracker (e.g. Bug should not be posted as Support tracker) 2. Review comments clarity 3. Naming conventions (e.g Sprint Name) 4. Tracking of previous sprint open items | DO | CO | 100% | 0.2 | 100% | 75 | 15
Total Score | [7 empty] | 1 |  |  | #DIV/0!
Time log | Time log by contributors,POD Owner and Product Owner | 100 | % | 1.All the contributors, POD owner and Product Owner (remote& Local) should log their efforts including the PTO | DO | CO | 100% | 0.4 | 100% | 100 | 40
| Time log by DO | 100 | % | Respective DO should log their efforts Separately inside each projects | CO | NA | 100% | 0.2 | 100% | 100 | 20
| Approval | 100 | % | L1 and L2 approval for team members time sheet | DO | CO | 100% | 0.4 | 100% | 100 | 40
Total Score | [7 empty] | 1 |  |  | 100

## DataSheet
Tracker | All Tracker | Meeting | Support | Story,Bug,Feature,Task | Testing
Total | 0 | 0 | 0 | 0 | 0
Planning | Resource Capacity | Capacity (hrs) | Estimated
| 5.5 | 440 | 0
Variance |  |  | #DIV/0!
0
UnMangable | Count | Variance
| 0 | #DIV/0! | 100
OverDue | Count | Variance
| 0 | #DIV/0! | 100
Workflow | Count | Variance
Impact Analysis | 0 | #DIV/0! | 0
Unit Testing | 0 | #DIV/0! | #DIV/0!
Code Review | 0 | #DIV/0! | #DIV/0!

## Data
# | Project | Tracker | Parent task | Status | Priority | Subject | Author | Assignee | Updated | Category | Target version | Start date | Due date | Estimated time | % Done | Created | Closed | Related issues | Description | Comment | Clarification | ExternalID | Actual start date | Severity | Actual End date | Occured | Impact | Impact Descrption | Probability | Score | Contingency plan | NC Type | RCA | Corrective Action | Outcome | ISO Pointer | W3H Analysis/Impact Result | Unit test result | Code review result | Test Results | Correction Action | Reason | Mitigation Plan | Test scenario/Cases | Risk Identified on | Department | Audit Type | Design | Priority | RCA Comment | PTO | Impact Description | Bug Type | Bug Classification | Sequence | Template
1173149 | DMO | Feature |  | New | Minor Impact | test1 | Shiva Reddy Srinivasa Reddy | Shiva Reddy Srinivasa Reddy | 18 Mar 2016 06:07 PM |  | test | 18 Mar 2016 |  |  | 0 | 18 Mar 2016 06:07 PM |  |  | test1
1173171 | DMO | Feature |  | New | Minor Impact | test33 | Shiva Reddy Srinivasa Reddy | Shiva Reddy Srinivasa Reddy | 18 Mar 2016 06:09 PM |  | test | 18 Mar 2016 |  |  | 0 | 18 Mar 2016 06:09 PM |  |  | test33