## CMD -Goals
KRA | KPA | Goal | Frequency | Purpose | Formula | Source | Actual | RAG
Business | SOW | Valid | Quarterly | Availability and validated of SOW | Available and Valid - 100 Not available or Valid - 0 | Drop Box | Green | Green
| Run Rate | 100 | Monthly | To measure the stability of number of billable resources | Run rate = Current Month / Previous Month *100 | SOW | 100 | Green
Delivery | Commitment Index / Turnaround Index | 100 | Sprint | To calculate the completion of agreed user stories | Commitment Index = No of issues completed/ No of issues planned *100. Turnaround = To be defined. | iNia | #DIV/0! | #DIV/0!
| Change Index (Percentage) | 3 | Sprint | To identify the number of change request received | No of CR's per Sprint or per delivery cycle | iNia | 0 | Green
| Effort Variance (Percentage) | 5 | Sprint | To calculate the variance between the planned and actual effort | EV = Planned - Actual / Planned *100 | iNia | #DIV/0! | #DIV/0!
| Velocity increase (percentage) | 5 | Quarterly | To identify the velocity and trend of increase/decrease. Goal it to get increased | Velocity = Previous sprint story points - Current sprint story points/ Previous sprint story points *100
| Quality Assurance Compliance | 90 | Monthly | To ensure the compliance with respect to quality |  | iNia | 95 | Green
| Client Escalation Index | 1 | Monthly | To calculate the no. of escalations addressed by the client | (No of escalation by client closed / No of escalation raised) *100 | iNia | #DIV/0! | #DIV/0!
| Client delivery satisfaction index | 4 | Sprint | To measure the customer's satisfaction on delivery of each sprint | (Weight age * Average of the particular section) + …+ n | Sprint review | 4.5 | Green
| Client Satisfaction Index | 4 | Quarterly | To measure the customer's satisfaction on the product or service rendered to them by OFS | (Weight age * Average of the particular section) + …+ n | CSAT Feedback Form | 4.5 | Green
Quality | Post Release Defects | ShowStopper = 0 Major=0 Minor = 2 | Sprint | To measure the defects in the product after release to the client | Ref. Calculation given below, but counting the actual major and minor based on the goal and consider 50% of variance | iNia | Green | Green
| Post release Code Quality | Major = 0 Minor = 2 | Sprint | To calculate the quality of the code | Ref. Calculation given below, but counting the actual major and minor based on the goal and consider 50% of variance | iNia | Green | Green
Resource | Resource allocation | 100 | Sprint | To ensure the number of resource allocated against required | Number of billable resource Number of resources deployed Allocation = (billable/ available)*100 | Resource Sheet | Red | Red
| Capacity (Skills) | 100 | Sprint | To ensure the skills of the resource allocated against required | Required capacity Available capacity (including shadow resource) Capacity = (Required/Available*100 | Capacity Sheet | Red | Red
| Resource burn down | 5 | Sprint | To ensure the resources not over burnt | burn down = Total hrs of working - Total hrs worked / Total hrs of working * 100 | iNia | 25 | Red
| Employee Satisfaction Index | 4 | Quarterly | To measure the employee satisfaction. |  | ESAT feedback form | 3 | Red
| Retention | 90 | Quarterly | To ensure the retention of the tem members | Retention = Number if team members changed/ (Number of team member changed - Total count) *100
Post release code quality |  |  |  |  | Post release defects
| Goal |  | Actual |  | Goal |  |  | Actual
Showstopper |  |  |  |  | 0 |  |  | 0
Major | 0 |  | 0 |  | 0 |  |  | 0
Minor | 2 |  | 0 |  | 2 |  |  | 0
| Major % |  | 0 |  | Major % |  |  | 0
| Indicator |  | Green |  | Indicator |  |  | Green
| Minor % |  | -100 |  | Minor % |  |  | -100
| Indicator |  | Green |  | Indicator |  |  | Green
| Overall |  | Green |  | Overall |  |  | Green
Resource Allocation
To be allocated | 5 | Allocated | 6
Capacity Required | 5 | Available | 5.5
Previous Month billable count | 5 | Current | 5
Last quarter billable count | 3 | Current quarter billable count | 5

## Delivery
Values
Row Labels | Sum of Estimated time | Sum of Spent time
CONN_Q3_S6_HCS1.0 | 201 | 192
Grand Total | 201 | 192
Values
Row Labels | Sum of Estimated time | Sum of Spent time
Arnab Kar | 32 | 23.5
Bhuvaneswari Rramakrishnan | 46 | 45.5
Satyanarayana Purushottama | 123 | 119
(blank) | 0 | 2
Grand Total | 201 | 190
Priority | (All)
Values
Count of # | Count of Status
13 | 13
Column Labels
| Bug | ChangeRequest | CodeReview | Feature | Grand Total
Count of # | 4 | 1 | 2 | 3 | 10

## Quality
# | (All)
Count of Priority | Column Labels
Row Labels | Defect | Grand Total
Major | 2 | 2
Minor | 2 | 2
Grand Total | 4 | 4
# | (All)
Count of Priority | Column Labels
Row Labels | CodeReview | Grand Total
Major | 1 | 1
Minor | 1 | 1
Grand Total | 2 | 2