## input
Category | Count | Status
|  | New | Inprogress | Resolved | Closed
Bug | 6 | 1 | 0 | 5 | 0
Story | 6 | 1 | 1 | 4 | 0
Improvement | 5 | 0 | 1 | 4 | 0
Technical task | 7 | 0 | 2 | 5 | 0
Total | 24 |  |  | 18
Progress | 6 | 75 | 25
Priority
|  | Major | Minor | Normal | Low
Bug |  | 6 | 0 | 0 | 0
Story |  | 6 | 0 | 0 | 0
Improvement |  | 5 | 0 | 0 | 0
Technical task |  | 7 | 0 | 0 | 0
Parent - Child
|  | Parent | Child
Bug |  | 0 | 0
Story |  | 0 | 1
Improvement |  | 0 | 0
Technical task |  | 0 | 6
Total |  | 0 | 7
Parent - Child
|  | New | Inprogress | Resolved | Closed
Parent |  | 0 | 0 | 0 | 0
Child |  | 0 | 2 | 5 | 0

## Data
# | Project | ExternalID | Tracker | Parent task | Status | Priority | Subject | Author | Assignee | Updated | Category | Target version | Start date | Due date | Estimated time | Spent time | % Done | Created | Closed | Related issues | Actual start date | Rank | Actual End date | Private
5199 | NG7 | NGTRUNK-16129 | Bug |  | New | Major | NGTRUNK-16129: Issue with counters smartitem name field when you start typing the name | Palanivel Nagarajan | Rethinam Thayanithy | 2014-05-20 15:58 |  | 18 FDN AUS 05/05/14 - 05/21/14 | 2014-05-05 | 2014-05-21 | 1 | 0 | 0 | 2014-05-20 15:58 | [5 empty] | 0
5196 | NG7 | NGTRUNK - 15594 | Bug |  | Resolved | Major | NGTRUNK - 15594: When the voice command processing window is closed and then re-launched, the control to it is lost. | Palanivel Nagarajan | Rethinam Thayanithy | 2014-05-21 17:33 |  | 18 FDN AUS 05/05/14 - 05/21/14 | 2014-05-05 | 2014-05-21 | 12 | 15.5 | 100 | 2014-05-20 15:55 |  |  | 2014-05-19 |  | 2014-05-20 | 0
5195 | NG7 | NGTRUNK-16218 | Story | Story #3758: NGTRUNK-15326: The system shall display the current patient name, DOB, Sex, Payor and Allergy alert (Latex specific) | Resolved | Major | NGTRUNK-16218: Patient age needs to be displayed on the patient header as per updated mockup | Palanivel Nagarajan | Rethinam Thayanithy | 2014-05-21 17:33 |  | 18 FDN AUS 05/05/14 - 05/21/14 | 2014-05-05 | 2014-05-21 | 2 | 2 | 100 | 2014-05-20 15:54 |  |  | 2014-05-20 |  |  | 0
4996 | NG7 | NGTRUNK-16072 | Bug |  | Resolved | Major | NGTRUNK-16072: NGTRUNK-15326 Needs to display the allergy as a sepearte entity in the patient header | Palanivel Nagarajan | Rethinam Thayanithy | 2014-05-21 17:34 |  | 18 FDN AUS 05/05/14 - 05/21/14 | 2014-05-05 | 2014-05-21 | 9 | 0 | 100 | 2014-05-19 15:15 |  |  | 2014-05-14 |  |  | 0
4995 | NG7 | NGTRUNK-16071 | Technical Task |  | Resolved | Major | NGTRUNK-16071: NGTRUNK-15326 Needs to display the MRN of the patient in the patient header. | Palanivel Nagarajan | Rethinam Thayanithy | 2014-05-21 16:57 |  | 18 FDN AUS 05/05/14 - 05/21/14 | 2014-05-05 | 2014-05-21 | 3 | 3 | 100 | 2014-05-19 15:14 |  |  | 2014-05-16 |  | 2014-05-19 | 0
4994 | NG7 | NGTRUNK-15809 | Improvement |  | Resolved | Major | NGTRUNK-15809: ngxtypeaheadpg: force matching selection | Palanivel Nagarajan | Rethinam Thayanithy | 2014-05-21 16:57 |  | 18 FDN AUS 05/05/14 - 05/21/14 | 2014-05-05 | 2014-05-21 | 5 | 7.5 | 100 | 2014-05-19 15:12 |  |  | 2014-05-13 |  | 2014-05-19 | 0
4993 | NG7 | NGTRUNK-15786 | Improvement |  | In Progress | Major | NGTRUNK-15786: new directive ngxTypeAheadMultiple to replace chosen | Palanivel Nagarajan | Karthik Easwaran | 2014-05-20 18:16 |  | 18 FDN AUS 05/05/14 - 05/21/14 | 2014-05-05 | 2014-05-21 | 36 | 24 | 90 | 2014-05-19 15:10 |  |  | 2014-05-12 |  |  | 0
4986 | NG7 | NGTRUNK-15807 | Bug |  | Resolved | Major | NGTRUNK-15807: clearing ngxtypeaheadpg doesn't reset list to show all results again | Ramkumar Ravikumar | Rethinam Thayanithy | 2014-05-21 16:58 |  | 18 FDN AUS 05/05/14 - 05/21/14 | 2014-05-05 | 2014-05-21 | 6 | 4.5 | 100 | 2014-05-19 13:15 |  |  | 2014-05-13 |  | 2014-05-19 | 0
4985 | NG7 | NGTRUNK - 15855 | Bug |  | Resolved | Major | 15855: Alerts Date Created field is not showing the local time created. | Ramkumar Ravikumar | Rethinam Thayanithy | 2014-05-21 17:31 |  | 18 FDN AUS 05/05/14 - 05/21/14 | 2014-05-19 |  | 3 | 3 | 100 | 2014-05-19 13:14 |  |  | 2014-05-15 |  | 2014-05-15 | 0
3774 | NG7 | NGTRUNK-15405 | Technical Task | Story #3758: NGTRUNK-15326: The system shall display the current patient name, DOB, Sex, Payor and Allergy alert (Latex specific) | In Progress | Major | NGTRUNK-15405: 1. Change patient header to show more details(DOB, Sex, Payor and allergy alert) | Ramkumar Ravikumar | Hentry Martin Paul muthuraj | 2014-05-20 17:39 |  | 18 FDN AUS 05/05/14 - 05/21/14 | 2014-05-05 | 2014-05-21 | 12 | 7 | 80 | 2014-05-08 18:59 |  |  | 2014-05-07 | 34772 |  | 0
3773 | NG7 | NGTRUNK-15406 | Technical Task | Story #3758: NGTRUNK-15326: The system shall display the current patient name, DOB, Sex, Payor and Allergy alert (Latex specific) | In Progress | Major | NGTRUNK-15406: Search and open patient will show the header with more info. | Ramkumar Ravikumar | Hentry Martin Paul muthuraj | 2014-05-20 18:13 |  | 18 FDN AUS 05/05/14 - 05/21/14 | 2014-05-05 | 2014-05-21 | 6 | 0 | 90 | 2014-05-08 18:59 |  |  | 2014-05-07 | 34773 | 2014-05-19 | 0
3772 | NG7 | NGTRUNK-15409 | Technical Task | Story #3758: NGTRUNK-15326: The system shall display the current patient name, DOB, Sex, Payor and Allergy alert (Latex specific) | Resolved | Major | NGTRUNK-15409: Show/hide the details of header when clicking on other menu item. | Ramkumar Ravikumar | Rethinam Thayanithy | 2014-05-21 17:31 |  | 18 FDN AUS 05/05/14 - 05/21/14 | 2014-05-05 | 2014-05-21 | 6 | 6 | 100 | 2014-05-08 18:59 |  |  | 2014-05-08 | 34776 | 2014-05-14 | 0
3771 | NG7 | NGTRUNK-15412 | Technical Task | Story #3756: NGTRUNK-15328:The system shall have the ability to display the patient profile picture from the "Patient Center" page. | Resolved | Major | NGTRUNK-15412: Create a mock layout for patient profile and show the picture | Ramkumar Ravikumar | Rethinam Thayanithy | 2014-05-21 17:31 |  | 18 FDN AUS 05/05/14 - 05/21/14 | 2014-05-05 | 2014-05-21 | 12 | 0 | 100 | 2014-05-08 18:59 |  |  | 2014-05-08 | 34779 | 2014-05-08 | 0
3770 | NG7 | NGTRUNK-15417 | Technical Task | Story #3765: NGTRUNK-14755: As a user, I want to be able to pick what roles can view my alerts if applicable. | Resolved | Major | NGTRUNK-15417: Remove required restriction from Roles list. | Ramkumar Ravikumar | Rethinam Thayanithy | 2014-05-21 17:32 |  | 18 FDN AUS 05/05/14 - 05/21/14 | 2014-05-09 | 2014-05-09 | 0.25 | 2 | 100 | 2014-05-08 18:59 |  |  | 2014-05-09 | 34784 | 2014-05-09 | 0
3768 | NG7 | NGTRUNK-15431 | Technical Task | Story #3762: NGTRUNK-15129: As a user, I want the Alerts tab view to be consistent with other tab views available under the patient. | Resolved | Major | NGTRUNK-15431: UI: Add a Patient Alert list | Ramkumar Ravikumar | Rethinam Thayanithy | 2014-05-21 17:32 |  | 18 FDN AUS 05/05/14 - 05/21/14 | 2014-05-05 | 2014-05-21 | 12 | 6 | 100 | 2014-05-08 18:59 |  |  | 2014-05-12 | 34796 | 2014-05-14 | 0
3765 | NG7 | NGTRUNK-14755 | Story |  | New | Major | NGTRUNK-14755: As a user, I want to be able to pick what roles can view my alerts if applicable. | Ramkumar Ravikumar |  | 2014-05-20 19:35 |  | 18 FDN AUS 05/05/14 - 05/21/14 | 2014-05-09 | 2014-05-09 | 0.25 | 0 | 100 | 2014-05-08 18:59 |  |  |  | 100 |  | 0
3764 | NG7 | NGTRUNK-11518 | Improvement |  | Resolved | Major | NGTRUNK-11518: UI: ngxTypeaheadPg type: selectadd (combo box functionality where user can create new) | Ramkumar Ravikumar | Rethinam Thayanithy | 2014-05-21 17:32 |  | 18 FDN AUS 05/05/14 - 05/21/14 | 2014-05-05 | 2014-05-21 | 18 | 17 | 100 | 2014-05-08 18:59 |  |  | 2014-05-08 | 100 | 2014-05-13 | 0
3763 | NG7 | NGTRUNK-14958 | Improvement |  | Resolved | Major | NGTRUNK-14958: add ng-required and required attributes for ngxTypeAheadPg | Ramkumar Ravikumar | Rethinam Thayanithy | 2014-05-21 17:32 |  | 18 FDN AUS 05/05/14 - 05/21/14 | 2014-05-05 | 2014-05-21 | 4 | 3 | 100 | 2014-05-08 18:59 |  |  | 2014-05-08 | 32084 | 2014-05-12 | 0
3762 | NG7 | NGTRUNK-15129 | Story |  | Resolved | Major | NGTRUNK-15129: As a user, I want the Alerts tab view to be consistent with other tab views available under the patient. | Ramkumar Ravikumar | Rethinam Thayanithy | 2014-05-21 17:34 |  | 18 FDN AUS 05/05/14 - 05/21/14 | 2014-05-05 | 2014-05-21 | 12 | 6.5 | 100 | 2014-05-08 18:59 |  |  | 2014-05-09 | 32069 |  | 0
3761 | NG7 | NGTRUNK-15132 | Improvement |  | Resolved | Major | NGTRUNK-15132:The NGX type ahead directive should be enhanced to include bold text in the search results. | Ramkumar Ravikumar | Rethinam Thayanithy | 2014-05-21 17:33 |  | 18 FDN AUS 05/05/14 - 05/21/14 | 2014-05-05 | 2014-05-21 | 3 | 5.5 | 100 | 2014-05-08 18:59 |  |  | 2014-05-06 | 32083 | 2014-05-19 | 0
3760 | NG7 | NGTRUNK-15193 | Bug |  | Resolved | Major | NGTRUNK-15193: Roles Smartfile Modal Categories tab text truncation issue | Ramkumar Ravikumar | Karthik Easwaran | 2014-05-20 17:37 |  | 18 FDN AUS 05/05/14 - 05/21/14 | 2014-05-05 | 2014-05-21 | 0 | 4 | 100 | 2014-05-08 18:59 |  |  | 2014-05-07 | 32080 | 2014-05-09 | 0
3758 | NG7 | NGTRUNK-15326 | Story |  | In Progress | Major | NGTRUNK-15326: The system shall display the current patient name, DOB, Sex, Payor and Allergy alert (Latex specific) | Ramkumar Ravikumar | Hentry Martin Paul muthuraj | 2014-05-20 18:13 |  | 18 FDN AUS 05/05/14 - 05/21/14 | 2014-05-05 | 2014-05-21 | 26 | 10 | 88 | 2014-05-08 18:59 |  |  | 2014-05-07 | 85 |  | 0
3756 | NG7 | NGTRUNK-15328 | Story |  | Resolved | Major | NGTRUNK-15328:The system shall have the ability to display the patient profile picture from the "Patient Center" page. | Ramkumar Ravikumar | Rethinam Thayanithy | 2014-05-21 16:57 |  | 18 FDN AUS 05/05/14 - 05/21/14 | 2014-05-05 | 2014-05-21 | 12 | 12.5 | 100 | 2014-05-08 18:59 |  |  | 2014-05-07 | 86 | 2014-05-09 | 0
3755 | NG7 | NGTRUNK-15370 | Story |  | Resolved | Major | NGTRUNK-15370: Patient Center: Add Timeline | Ramkumar Ravikumar | Rethinam Thayanithy | 2014-05-21 16:57 |  | 18 FDN AUS 05/05/14 - 05/21/14 | 2014-05-05 | 2014-05-21 | 15 | 16.5 | 100 | 2014-05-08 18:59 |  |  | 2014-05-08 | 97 | 2014-05-19 | 0