## Account Dashboard
Executive Dashboard
Account | Zirus | Project | Zerp
CO | Fazurul | DO | Michel
Project | Delivery | Quality | Resourcce
Zerp | #N/A | Red | Red

## Goals
KRA | KPA | Goal | Unit | Tolerance | Frequency | Purpose | Formula | Source | Actual | RAG
Delivery | Commitment Index / Turnaround Index | 100 | % |  | Sprint | To calculate the completion of agreed user stories | Commitment Index = No of issues completed/ No of issues planned *100. Turnaround = To be defined. | iNia | #DIV/0! | #DIV/0!
| Effort Variance (Percentage) | 0 | % | +/- 5% | Sprint | To calculate the variance between the planned and actual effort | EV = Planned - Actual / Planned *100 | iNia | #DIV/0! | #DIV/0!
| Increase in Velocity | 5 | % | +/- 5% | Sprint | To identify the velocity and trend of increase/decrease. Goal it to get increased | Velocity = Previous sprint story points - Current sprint story points/ Previous sprint story points *100 | iNia | Green | Green
| Quality Assurance Compliance | 90 | % |  | Monthly | To ensure the compliance with respect to quality |  | iNia | 95 | Green
| Client Escalation Index | Major=0 Minor = 1 | Unit |  | Quarterly | To calculate the no. of escalations addressed by the client | (No of escalation by client closed / No of escalation raised) *100 | iNia | Green | Green
Quality | Post Release Defects | Major=0 Minor = 2 Cosmetic = 4 | Unit |  | Sprint | To measure the defects in the product after release to the client | Ref. Calculation given below, but counting the actual major and minor based on the goal and consider 50% of variance | iNia | Green | Green
| Pre Release Code Quality | Major = 0 Minor = 2 Cosmatic = 8 | Unit |  | Sprint | To calculate the quality of the code | Ref. Calculation given below, but counting the actual major and minor based on the goal and consider 50% of variance | iNia | Green | Green
Resource | Resource allocation | 100 | % |  | Sprint | To ensure the number of resource allocated against required | Number of billable resource Number of resources deployed Allocation = (billable/ available)*100 | Resource Sheet | Green | Green
| Capacity (Skills) | 100 | % |  | Sprint | To ensure the skills of the resource allocated against required | Required capacity Available capacity (including shadow resource) Capacity = (Required/Available*100 | Capacity Sheet | Green | Green
| Resource burn down | 0 | % | +/- 10% | Sprint | To ensure the resources not over burnt | burn down = Total hrs of working - Total hrs worked / Total hrs of working * 100 | iNia | -100 | Red
| Employee Satisfaction Index |  | % |  | Quarterly | To measure the employee satisfaction. |  | ESAT feedback form
| Retention | 100 | % |  | Quarterly | To ensure the retention of the tem members | Retention = Number if team members changed/ (Number of team member changed - Total count) *100
Code Quality | [6 empty] | Defects
| Goal |  |  |  | Actual |  | Goal |  |  | Actual
Major | 0 |  |  |  | 0 |  | 0 |  |  | 0
Minor | 2 |  |  |  | 0 |  | 2 |  |  | 0
Cosmetic | 0 |  |  |  | 0 |  | 4 |  |  | 0
| Major % |  |  |  | 0 |  | Major % |  |  | 0
| Indicator |  |  |  | Green |  | Indicator |  |  | Green
| Minor % |  |  |  | -100 |  | Minor % |  |  | -100
| Indicator |  |  |  | Green |  | Indicator |  |  | Green
| Overall |  |  |  | Green |  | Overall |  |  | Green
Escalation | [6 empty] | Velocity | Story Points
| Goal |  |  |  | Actual |  | Planned Velocity | 20
Major | 0 |  |  |  | 0
Minor | 2 |  |  |  | 0
| Major % |  |  |  | 0
| Indicator |  |  |  | Green
| Minor % |  |  |  | -100
| Indicator |  |  |  | Green
| Overall |  |  |  | Green
Resource Allocation
To be allocated | 6 | Allocated |  |  | 9
Capacity Required | 6 | Available |  |  | 7

## Metrics
| Target version | Data
| Invoice22 DC5 - Report2 DC2(10-Dec-2014 to 23-Dec-2014) |  | Total Sum of Estimated time | Total Sum of Spent time
| Sum of Estimated time | Sum of Spent time
Total | 649.5 | 622.2 | 649.5 | 622.2
Data
Author | Sum of Estimated time | Sum of Spent time
Dineshkumar Ramasamy | 29 | 28
Kalidass Sethuraman | 57 | 57
Kumaresan Krishnakumari | 113.5 | 104.5
Michael Arockiya Samy | 68 | 65.5
Millton Vinothkumar Raja | 374 | 359.2
Vinothini Rajamanickam | 8 | 8
(blank)
Grand Total | 649.5 | 622.2
Priority | (All)
Data
| Count of Status | Count of #
Total | 108 | 108
Count of # | Tracker
| Code Review | Feature | Support | Task | (blank) | Grand Total
Total | 20 | 84 | 3 | 1 |  | 108
# | (All)
Count of Tracker | Priority
| Minor Impact | (blank) | Grand Total
Total | 108 |  | 108