## Dashboard
Executive Dashboard
Delivery | Quality | Resource
Red | #N/A | Green

## Goals
Sprint | Release 5.8.2
KRA | KPA | Goal | Unit | Actual | RAG
Delivery | Commitment Index / Turnaround Index | 100 | % | 51.0204 | Red
| Effort Variance (Percentage) | 20 | % | 1.0163 | Green
| Audit Compliance | 2 | Unit | 8 | Red
| Client Escalation Index | Major=0 Minor = 1 | Unit | Green | Green
Quality | Post Release Defects | Showstopper - 0 Major - 2 Minor - 5 Cosmetic - 10 | Unit | Green | Green
| Post Release Code Quality | Major = 0 Minor = 2 Cosmetic = 8 | Unit | Green | Green
Resource | Resource allocation | 100 | % | Green | Green
| Capacity (Skills) | 100 | % | Green | Green
| Resource burn down | 20 | % | -81.8042 | Red
Code Quality | [5 empty] | Defects
| Goal |  |  |  | Actual | Goal |  | Actual
Show Stopper | [5 empty] | 0 |  | 0
Major | 0 |  |  |  | 0 | 2 |  | 0
Minor | 2 |  |  |  | 0 | 5 |  | 0
Cosmetic | 0 |  |  |  | 0 | 10 |  | 0
[6 empty] | ShowStopper % |  | 0
[6 empty] | Indicator |  | Green
| Major % |  |  |  | 0 | Major % |  | -100
| Indicator |  |  |  | Green | Indicator |  | Green
| Minor % |  |  |  | -100 | Minor % |  | -100
| Indicator |  |  |  | Green | Indicator |  | Green
| Overall |  |  |  | Green | Overall |  | Green
Escalation | [5 empty] | Velocity | Story Points
| Goal |  |  |  | Actual | Planned Velocity | 20
Major | 0 |  |  |  | 0
Minor | 2 |  |  |  | 0
| Major % |  |  |  | 0
| Indicator |  |  |  | Green
| Minor % |  |  |  | -100
| Indicator |  |  |  | Green
| Overall |  |  |  | Green
Resource Allocation
To be allocated | 5 | Allocated |  |  | 6
Capacity Required | 5 | Available |  |  | 5.5

## Chart
Count of #
Tracker
Action | 2
Audit | 7
Bug | 63
Code Review | 5
DAA | 8
Feature | 1
Meetings | 9
Support | 1
Training | 2
Total Result | 98
Data
Tracker | Sum of Estimated time | Sum of Spent time
Action | 16 | 16
Audit |  | 0
Bug | 770.5 | 793.95
Code Review | 16.75 | 1.5
DAA |  | 0
Feature |  | 0
Meetings | 48.13 | 48.71
Support | 6 | 6
Training | 6.5 | 6.5
Grand Total | 863.88 | 872.66
Data
Tracker | Count of # | Count of W3H Analysis/Impact Result | Count of Unit test result | Count of Code review result
Bug | 63 | 32 | 34 | 32
Feature | 1 |  | 1 | 1
Grand Total | 64 | 32 | 35 | 33

## Risk
Tracker | Subject | Staus | Impact | Probability | Identified on | Mitigation | Score
Meetings | Retro Meeting | Closed | 0 | 0 | 0 | 0 | 0
Code Review | ANALYST-9217; | In Progress | 0 | 0 | 0 | 0 | 0
Bug | ANALYST-9217; | In Progress | 0 | 0 | 0 | 0 | 0
Bug | Analyst-9269 | In Progress | 0 | 0 | 0 | 0 | 0
Code Review | ANALYST-9038; | In Progress | 0 | 0 | 0 | 0 | 0
Bug | ANALYST-9051; | In Progress | 0 | 0 | 0 | 0 | 0
Code Review | CODE REVIEW - ANALYST-9248 (Analyst does not complain at compile time when a group rule field is populated with a non-boolean) | New | 0 | 0 | 0 | 0 | 0
Bug | ANALYST-9248 (Analyst does not complain at compile time when a group rule field is populated with a non-boolean) | In Progress | 0 | 0 | 0 | 0 | 0
Bug | Leave on 26th March 2015 | New | 0 | 0 | 0 | Not Applicable | 0
Bug | Executing the Sanity testcases | Closed | 0 | 0 | 0 | 0 | 0
Bug | ANALYST-9247; | Closed | 0 | 0 | 0 | 0 | 0
Feature | Leave On 26th March 2015 | Closed | 0 | 0 | 0 | Not Applicable | 0
Training | KT for Aishwarya | In Progress | 0 | 0 | 0 | 0 | 0
Meetings | CDA- Audit | In Progress | 0 | 0 | 0 | 0 | 0
Bug | ANALYST-9273 ( Looping associations is lost when the map is loaded) | In Progress | 0 | 0 | 0 | 0 | 0
Bug | ANALYST-9267; | Closed | 0 | 0 | 0 | 0 | 0
Action | Planned Leave | Closed | 0 | 0 | 0 | 0 | 0
Bug | Analysing and working on the issue mentioned by phillip | Closed | 0 | 0 | 0 | 0 | 0
Bug | Project Discussion | In Progress | 0 | 0 | 0 | 0 | 0
Audit | iNia is not effectively used. | New | 0 | 0 | 0 | 0 | 0
Audit | PMP is not updated and review by PM for long time | New | 0 | 0 | 0 | 0 | 0
Audit | nas rights not removed for Ganesh | New | 0 | 0 | 0 | 0 | 0
Audit | DAA findings are not closed for long time | New | 0 | 0 | 0 | 0 | 0
Audit | Metrics | New | 0 | 0 | 0 | 0 | 0
Audit | Retro meeting not conducted for last sprint and MOM not evidenced | New | 0 | 0 | 0 | 0 | 0
Meetings | Issue discussion with Ramya | Closed | 0 | 0 | 0 | 0 | 0
Meetings | Issue discussion with Ramya(Duplicated) | Closed | 0 | 0 | 0 | 0 | 0
Bug | ANALYST-9248 (Analyst does not complain at compile time when a group rule field is populated with a non-boolean) | In Progress | 0 | 0 | 0 | 0 | 0
Bug | Working On Issue 6493 | In Progress | 0 | 0 | 0 | 0 | 0
Audit | Facilitation Audit Dated 24-Mar-2015 | New | 0 | 0 | 0 | 0 | 0
Bug | ANALYST-9258 (CLONE - Global Element Exception when trying to create a interface with xml file ) | In Progress | 0 | 0 | 0 | 0 | 0
Bug | ANALYST-9030; | Closed | 0 | 0 | 0 | 0 | 0
Bug | Analyst-9260 | Closed | 0 | 0 | 0 | 0 | 0
Bug | CDA Stand-Up Meeting | Closed | 0 | 0 | 0 | 0 | 0
Bug | Working on the Contivo product | In Progress | 0 | 0 | 0 | 0 | 0
Bug | KT Session | In Progress | 0 | 0 | 0 | 0 | 0
Code Review | Code Review for Mar-2015 | In Progress | 0 | 0 | 0 | 0 | 0
Bug | ANALYST-9238; | In Progress | 0 | 0 | 0 | 0 | 0
Bug | ANALYST-9231 ("Output the mapping rule value only if the parent group exists" isn't working correctly) | Closed | 0 | 0 | 0 | 0 | 0
Bug | Issue 9245 | Closed | 0 | 0 | 0 | Ticket moved to next sprint. | 0
Bug | ANALYST-9263; | Closed | 0 | 0 | 0 | 0 | 0
Meetings | Analyst - 9253 Discussion with bestus | Closed | 0 | 0 | 0 | 0 | 0
Bug | ANALYST-9268 ("moveToChildGroup: commit failed while moving from group rateplan" when inserting into a database ) | In Progress | 0 | 0 | 0 | 0 | 0
Bug | ANALYST-9226; | Closed | 0 | 0 | 0 | 0 | 0
Bug | ANALYST-9257 CLONE - Opening a map in Analyst newer than 5.3 causes a NumberFormatException | In Progress | 0 | 0 | 0 | 0 | 0
Bug | Analyst-9252 | In Progress | 0 | 0 | 0 | 0 | 0
Bug | Analyst-9266 | Closed | 0 | 0 | 0 | 0 | 0
Bug | ANALYST-9251; | In Progress | 0 | 0 | 0 | 0 | 0
Bug | ANALYST-9253 (Cannot generate the Java transformation throws stack overflow exception) | Suspended | 0 | 0 | 0 | Assigned to onsite person | 0
Bug | Executing the sanity testcases for repo & Prism | Closed | 0 | 0 | 0 | 0 | 0
Bug | Leave | Closed | 0 | 0 | 0 | N/A | 0
Bug | Working on resolved issue | Closed | 0 | 0 | 0 | 0 | 0
Bug | Testing resolved issues | Closed | 0 | 0 | 0 | Testing | 0
Bug | Issue-9264 | In Progress | 0 | 0 | 0 | 0 | 0
Bug | ANALYST-9063; | Closed | 0 | 0 | 0 | 0 | 0
Bug | ANALYST-9265 (Mapped value doesn't get outputted for Java transformation if the logic group has present) | In Progress | 0 | 0 | 0 | 0 | 0
Bug | Analyst-9012 | Suspended | 0 | 0 | 0 | since the issue is will be fixed in the future prism.suspending this issue. | 0

## Action
Tracker | Subject | Staus | Start Date | Due Date
Meetings | Retro Meeting | Closed | 2015-03-31 | 2015-03-31
Code Review | ANALYST-9217; | In Progress | 2015-03-31 | 2015-04-02
Bug | ANALYST-9217; | In Progress | 2015-03-31 | 2015-04-02
Bug | Analyst-9269 | In Progress | 2015-03-31 | 2015-04-02
Code Review | ANALYST-9038; | In Progress | 2015-03-31 | 2015-04-02
Bug | ANALYST-9051; | In Progress | 2015-03-31 | 2015-04-02
Code Review | CODE REVIEW - ANALYST-9248 (Analyst does not complain at compile time when a group rule field is populated with a non-boolean) | New | 2015-03-31 | 2015-04-02
Bug | ANALYST-9248 (Analyst does not complain at compile time when a group rule field is populated with a non-boolean) | In Progress | 2015-03-31 | 0
Bug | Leave on 26th March 2015 | New | 2015-03-31 | 0
Bug | Executing the Sanity testcases | Closed | 2015-03-26 | 2015-03-26
Bug | ANALYST-9247; | Closed | 2015-03-27 | 2015-03-27
Feature | Leave On 26th March 2015 | Closed | 2015-03-26 | 2015-04-02
Training | KT for Aishwarya | In Progress | 2015-03-26 | 2015-03-26
Meetings | CDA- Audit | In Progress | 2015-03-26 | 2015-04-30
Bug | ANALYST-9273 ( Looping associations is lost when the map is loaded) | In Progress | 2015-03-24 | 2015-03-24
Bug | ANALYST-9267; | Closed | 2015-03-26 | 2015-03-26
Action | Planned Leave | Closed | 2015-03-25 | 2015-03-26
Bug | Analysing and working on the issue mentioned by phillip | Closed | 2015-03-25 | 2015-03-26
Bug | Project Discussion | In Progress | 2015-03-25 | 2015-03-27
Audit | iNia is not effectively used. | New | 2015-03-25 | 2015-04-30
Audit | PMP is not updated and review by PM for long time | New | 2015-03-24 | 0
Audit | nas rights not removed for Ganesh | New | 2015-03-24 | 0
Audit | DAA findings are not closed for long time | New | 2015-03-24 | 0
Audit | Metrics | New | 2015-03-24 | 0
Audit | Retro meeting not conducted for last sprint and MOM not evidenced | New | 2015-03-24 | 0
Meetings | Issue discussion with Ramya | Closed | 2015-03-24 | 0
Meetings | Issue discussion with Ramya(Duplicated) | Closed | 2015-03-24 | 2015-03-24
Bug | ANALYST-9248 (Analyst does not complain at compile time when a group rule field is populated with a non-boolean) | In Progress | 2015-03-24 | 2015-03-24
Bug | Working On Issue 6493 | In Progress | 2015-03-24 | 2015-03-27
Audit | Facilitation Audit Dated 24-Mar-2015 | New | 2015-03-23 | 2015-04-10
Bug | ANALYST-9258 (CLONE - Global Element Exception when trying to create a interface with xml file ) | In Progress | 2015-03-24 | 0
Bug | ANALYST-9030; | Closed | 2015-03-24 | 2015-03-25
Bug | Analyst-9260 | Closed | 2015-03-23 | 2015-03-27
Bug | CDA Stand-Up Meeting | Closed | 2015-03-23 | 2015-03-25
Bug | Working on the Contivo product | In Progress | 2015-03-23 | 2015-04-30
Bug | KT Session | In Progress | 2015-03-23 | 2015-04-30
Code Review | Code Review for Mar-2015 | In Progress | 2015-03-23 | 2015-04-30
Bug | ANALYST-9238; | In Progress | 2015-03-23 | 2015-03-31
Bug | ANALYST-9231 ("Output the mapping rule value only if the parent group exists" isn't working correctly) | Closed | 2015-03-31 | 2015-04-02
Bug | Issue 9245 | Closed | 2015-03-20 | 2015-03-27
Bug | ANALYST-9263; | Closed | 2015-03-18 | 2015-04-03
Meetings | Analyst - 9253 Discussion with bestus | Closed | 2015-03-18 | 2015-03-20
Bug | ANALYST-9268 ("moveToChildGroup: commit failed while moving from group rateplan" when inserting into a database ) | In Progress | 2015-03-18 | 2015-03-18
Bug | ANALYST-9226; | Closed | 2015-03-19 | 2015-03-24
Bug | ANALYST-9257 CLONE - Opening a map in Analyst newer than 5.3 causes a NumberFormatException | In Progress | 2015-03-17 | 2015-03-20
Bug | Analyst-9252 | In Progress | 2015-03-17 | 2015-03-25
Bug | Analyst-9266 | Closed | 2015-03-16 | 2015-04-03
Bug | ANALYST-9251; | In Progress | 2015-03-16 | 2015-04-01
Bug | ANALYST-9253 (Cannot generate the Java transformation throws stack overflow exception) | Suspended | 2015-03-31 | 2015-04-02
Bug | Executing the sanity testcases for repo & Prism | Closed | 2015-03-16 | 2015-03-20
Bug | Leave | Closed | 2015-03-16 | 2015-03-20
Bug | Working on resolved issue | Closed | 2015-03-13 | 2015-03-13
Bug | Testing resolved issues | Closed | 2015-03-13 | 2015-03-20
Bug | Issue-9264 | In Progress | 2015-03-13 | 2015-03-20
Bug | ANALYST-9063; | Closed | 2015-03-13 | 2015-04-10
Bug | ANALYST-9265 (Mapped value doesn't get outputted for Java transformation if the logic group has present) | In Progress | 2015-03-13 | 2015-03-13
Bug | Analyst-9012 | Suspended | 2015-03-12 | 2015-04-03

## Data
# | Project | Tracker | Parent task | Status | Priority | Subject | Author | Assignee | Updated | Category | Target version | Start date | Due date | Estimated time | Spent time | % Done | Created | Closed | Related issues | Clarification | Actual start date | Actual End date | Occured | Impact | Impact Descrption | Probability | Score | Contingency plan | NC Type | RCA | Outcome | ISO Pointer | W3H Analysis/Impact Result | Unit test result | Code review result | Suspend reason | Correction Action | Mitigation Plan | Re-Open reason | Risk Identified on | Private | Private2
65388 | CDA | Meetings |  | Closed | Minor Impact | Retro Meeting | Rushendra Babu Natarajan | Rushendra Babu Natarajan | 2015-03-31 20:21 |  | Release 5.8.2 | 2015-03-31 | 2015-03-31 | 1 | 1 | 100 | 2015-03-31 20:20 | 2015-03-31 20:21 |  |  | 2015-03-31 | [19 empty] | 0
65325 | CDA | Code Review | Bug #65323: ANALYST-9217; | In Progress | Low | ANALYST-9217; | Sharath Jaganathan | Ramya Sakthivelu | 2015-03-31 16:31 |  | Release 5.8.2 | 2015-03-31 | 2015-04-02 | 0.25 | 0 | 0 | 2015-03-31 16:31 |  |  |  | 2015-03-31 | [19 empty] | 0
65323 | CDA | Bug |  | In Progress | Low | ANALYST-9217; | Sharath Jaganathan | Sharath Jaganathan | 2015-04-01 11:08 |  | Release 5.8.2 | 2015-03-31 | 2015-04-02 | 4 | 2.75 | 70 | 2015-03-31 16:30 |  |  | NO clarification needed since it is a Gui issue and just enabled the interfaceStructureChange property to XML attributes too. | 2015-03-31 | [11 empty] | NO major impact will occur due to this fix since it is a gui issue | NO unit test is required | [6 empty] | 0
65322 | CDA | Code Review | Bug #65320: Analyst-9269 | In Progress | High | ANALYST-9269; | Sharath Jaganathan | Ramya Sakthivelu | 2015-03-31 16:27 |  | Release 5.8.2 | 2015-03-31 | 2015-04-02 | 0.25 | 0 | 0 | 2015-03-31 16:27 |  |  |  | 2015-03-31 | [19 empty] | 0
65320 | CDA | Bug |  | In Progress | High | Analyst-9269 | Sharath Jaganathan | Sharath Jaganathan | 2015-04-01 11:08 |  | Release 5.8.2 | 2015-03-31 | 2015-04-02 | 6 | 4 | 70 | 2015-03-31 16:26 |  |  | No Clarification needed | 2015-03-31 | [11 empty] | No impact analysis is needed since it is gui issue. | Tested with changing the rule and then running all transforms | [6 empty] | 0
65319 | CDA | Code Review | Bug #63998: ANALYST-9238; | In Progress | Minor Impact | ANALYST-9038; | Sharath Jaganathan | Ramya Sakthivelu | 2015-03-31 16:24 |  | Release 5.8.2 | 2015-03-31 | 2015-04-02 | 0.25 | 0 | 0 | 2015-03-31 16:24 |  |  |  | 2015-03-31 | [19 empty] | 0
65317 | CDA | Bug | Bug #62984: ANALYST-9251; | In Progress | Minor Impact | ANALYST-9051; | Sharath Jaganathan | Ramya Sakthivelu | 2015-03-31 16:23 |  | Release 5.8.2 | 2015-03-31 | 2015-04-02 | 0.25 | 0 | 0 | 2015-03-31 16:23 |  |  |  | 2015-03-31 | [19 empty] | 0
65277 | CDA | Code Review | Bug #65275: ANALYST-9248 (Analyst does not complain at compile time when a group rule field is populated with a non-boolean) | New | Minor Impact | CODE REVIEW - ANALYST-9248 (Analyst does not complain at compile time when a group rule field is populated with a non-boolean) | Rushendra Babu Natarajan | Ramya Sakthivelu | 2015-03-31 13:12 |  | Release 5.8.2 | 2015-03-31 |  |  | 0 | 0 | 2015-03-31 13:12 | [23 empty] | 0
65275 | CDA | Bug |  | In Progress | Minor Impact | ANALYST-9248 (Analyst does not complain at compile time when a group rule field is populated with a non-boolean) | Rushendra Babu Natarajan | Rushendra Babu Natarajan | 2015-03-31 20:22 |  | Release 5.8.2 | 2015-03-31 |  | 5.5 | 5.5 | 0 | 2015-03-31 13:11 |  |  | Clarrified for the unknown values moving to Target GRF. | 2015-03-31 | [19 empty] | 0
65048 | CDA | Bug |  | New | Minor Impact | Leave on 26th March 2015 | Phani Madhav Atchyutanna Jagan Rao | Phani Madhav Atchyutanna Jagan Rao | 2015-03-30 15:43 |  | Release 5.7 | 2015-03-26 | 2015-03-26 | 8 | 8 | 0 | 2015-03-30 15:43 |  |  | Not Applicable | 2015-03-26 | 2015-03-26 | [11 empty] | Not Applicable | Not Applicable | Not Applicable |  |  |  |  | 0
64793 | CDA | Bug |  | Closed | Minor Impact | Executing the Sanity testcases | Rammiyajoya Allwin Roegers | Rammiyajoya Allwin Roegers | 2015-03-30 12:47 |  | Release 6.0 | 2015-03-27 | 2015-03-27 | 7 | 7 | 0 | 2015-03-27 11:38 | 2015-03-30 12:47 | [22 empty] | 0
64778 | CDA | Bug |  | Closed | High | ANALYST-9247; | Sharath Jaganathan | Sharath Jaganathan | 2015-03-31 10:54 |  | Release 6.0 | 2015-03-26 | 2015-04-02 | 15.3 | 15.3 | 100 | 2015-03-27 11:05 | 2015-03-31 10:54 |  | NO clarification needed | 2015-03-26 | 2015-03-30 | [10 empty] | NO impact analysis is needed since it is a GUI issue | tested with both visible and invisible mapped fields in the detail pane for both target and the source side | Reviewer:ramya Asked to introduce a boolean for both getinvisiblesourecmappedfields() and getinvisibletargetmappedfields() in maptestinginfodialog.java,whenever the call is coming from the Navigation mapped fields.since the both methods are called by multiple methods,we have introduced a boolean and iterated the both visible and invisible mapped fields | [5 empty] | 0
64762 | CDA | Feature |  | Closed | Minor Impact | Leave On 26th March 2015 | Phani Madhav Atchyutanna Jagan Rao | Phani Madhav Atchyutanna Jagan Rao | 2015-03-27 10:42 |  | Release 6.0 | 2015-03-26 | 2015-03-26 |  | 0 | 0 | 2015-03-27 10:41 | 2015-03-27 10:42 |  | Not Applicable | [13 empty] | Not Applicable | Not Applicable | Not Applicable |  |  |  |  | 0
64620 | CDA | Training |  | In Progress | Minor Impact | KT for Aishwarya | Rammiyajoya Allwin Roegers | Rammiyajoya Allwin Roegers | 2015-04-01 16:34 |  | Release 5.8.2 | 2015-03-26 | 2015-04-30 | 3.5 | 3.5 | 0 | 2015-03-26 12:49 | [23 empty] | 0
64613 | CDA | Meetings |  | In Progress | Minor Impact | CDA- Audit | Ramya Sakthivelu | Ramya Sakthivelu | 2015-03-26 12:18 |  | Release 6.0 | 2015-03-24 | 2015-03-24 | 2 | 2 | 90 | 2015-03-26 12:18 |  |  |  | 2015-03-24 | [19 empty] | 0
64612 | CDA | Bug |  | In Progress | Critical Impact | ANALYST-9273 ( Looping associations is lost when the map is loaded) | Ramya Sakthivelu | Ramya Sakthivelu | 2015-03-26 12:13 |  | Release 6.0 | 2015-03-26 | 2015-03-26 | 8 | 8.5 | 0 | 2015-03-26 12:13 |  |  |  | 2015-03-25 | [19 empty] | 0
64602 | CDA | Bug |  | Closed | Low | ANALYST-9267; | Sharath Jaganathan | Sharath Jaganathan | 2015-03-27 11:03 |  | Release 6.0 | 2015-03-25 | 2015-03-26 | 8.4 | 8.4 | 100 | 2015-03-26 10:53 | 2015-03-27 11:03 |  | No Clarification needed | 2015-03-25 | 2015-03-26 | [10 empty] | The fix might not cause any impact in the product since,we corrected the access of the object,which is suspected to be null inside the null check. | Tested with all possible uses cases by modifying the rule,and and also ran the regression . | Reviewer:Ramya verified and added the object inside the null check loop in Tree#hasNext() | [5 empty] | 0
64595 | CDA | Action |  | Closed | Minor Impact | Planned Leave | Prisla Sabatini Irudayaraj | Prisla Sabatini Irudayaraj | 2015-03-26 10:19 |  | Release 6.0 | 2015-03-25 | 2015-03-26 | 8 | 8 | 100 | 2015-03-26 10:18 | 2015-03-26 10:18 | [22 empty] | 0
64584 | CDA | Bug |  | Closed | Minor Impact | Analysing and working on the issue mentioned by phillip | Rushendra Babu Natarajan | Rushendra Babu Natarajan | 2015-03-31 13:06 |  | Release 6.0 | 2015-03-25 | 2015-03-27 | 4 | 4 | 100 | 2015-03-25 20:53 | 2015-03-31 13:06 |  | No need | 2015-03-25 | 2015-03-27 | [10 empty] | Might have no | Tested this at the time of Server start up. The code was called at that time only but, we couldn't reproduce the isuue. | Issue couldn't reproduce. | [5 empty] | 0
64430 | CDA | Bug |  | In Progress | Minor Impact | Project Discussion | Prisla Sabatini Irudayaraj | Prisla Sabatini Irudayaraj | 2015-04-01 10:43 |  |  | 2015-03-25 | 2015-04-30 | 2 | 1 | 0 | 2015-03-25 09:43 |  |  | NA | [12 empty] | NA | NA | NA | [5 empty] | 0
64420 | CDA | Audit | Audit #64165: Facilitation Audit Dated 24-Mar-2015 | New | Minor Impact | iNia is not effectively used. | Michael Arockiya Samy | Bestus Paul Daniel Franklin Inbaraj | 2015-03-26 10:13 |  |  | 2015-03-24 |  |  | 0 | 0 | 2015-03-24 21:34 | [13 empty] | NC | 4.2.4 | [8 empty] | 0
64419 | CDA | Audit | Audit #64165: Facilitation Audit Dated 24-Mar-2015 | New | Minor Impact | PMP is not updated and review by PM for long time | Michael Arockiya Samy | Bestus Paul Daniel Franklin Inbaraj | 2015-03-26 10:14 |  |  | 2015-03-24 |  |  | 0 | 0 | 2015-03-24 21:33 | [13 empty] | NC | 7.1 | [8 empty] | 0
64418 | CDA | Audit | Audit #64165: Facilitation Audit Dated 24-Mar-2015 | New | Minor Impact | nas rights not removed for Ganesh | Michael Arockiya Samy | Bestus Paul Daniel Franklin Inbaraj | 2015-03-26 10:15 |  |  | 2015-03-24 |  |  | 0 | 0 | 2015-03-24 21:33 | [13 empty] | NC | 6.3 & 7.5.3 | [8 empty] | 0
64417 | CDA | Audit | Audit #64165: Facilitation Audit Dated 24-Mar-2015 | New | Minor Impact | DAA findings are not closed for long time | Michael Arockiya Samy | Bestus Paul Daniel Franklin Inbaraj | 2015-03-26 10:16 |  |  | 2015-03-24 |  |  | 0 | 0 | 2015-03-24 21:32 | [13 empty] | NC | 8.22 &8.5.2 | [8 empty] | 0
64416 | CDA | Audit | Audit #64165: Facilitation Audit Dated 24-Mar-2015 | New | Minor Impact | Metrics | Michael Arockiya Samy | Bestus Paul Daniel Franklin Inbaraj | 2015-03-26 10:28 |  |  | 2015-03-24 |  |  | 0 | 0 | 2015-03-24 21:31 | [13 empty] | NC | 8.2 | [8 empty] | 0
64414 | CDA | Audit | Audit #64165: Facilitation Audit Dated 24-Mar-2015 | New | Minor Impact | Retro meeting not conducted for last sprint and MOM not evidenced | Michael Arockiya Samy | Bestus Paul Daniel Franklin Inbaraj | 2015-03-26 10:29 |  |  | 2015-03-24 |  |  | 0 | 0 | 2015-03-24 21:22 | [13 empty] | NC | [9 empty] | 0
64320 | CDA | Meetings |  | Closed | Minor Impact | Issue discussion with Ramya | Rushendra Babu Natarajan | Rushendra Babu Natarajan | 2015-03-31 13:01 |  | Release 6.0 | 2015-03-24 | 2015-03-24 | 1 | 1 | 100 | 2015-03-24 20:19 | 2015-03-31 13:01 |  |  | 2015-03-24 | [19 empty] | 0
64319 | CDA | Meetings |  | Closed | Minor Impact | Issue discussion with Ramya(Duplicated) | Rushendra Babu Natarajan | Rushendra Babu Natarajan | 2015-03-24 20:21 |  | Release 6.0 | 2015-03-24 | 2015-03-24 | 0 | 0 | 100 | 2015-03-24 20:16 | 2015-03-24 20:16 |  |  | 2015-03-24 | [19 empty] | 0
64317 | CDA | Bug |  | In Progress | Minor Impact | ANALYST-9248 (Analyst does not complain at compile time when a group rule field is populated with a non-boolean) | Rushendra Babu Natarajan |  | 2015-03-24 20:13 |  |  | 2015-03-24 | 2015-03-27 | 10 | 6 | 30 | 2015-03-24 20:13 |  |  |  | 2015-03-24 | [19 empty] | 0
64194 | CDA | Bug |  | In Progress | Minor Impact | Working On Issue 6493 | Phani Madhav Atchyutanna Jagan Rao | Phani Madhav Atchyutanna Jagan Rao | 2015-03-31 12:38 |  | Release 5.8.2 | 2015-03-23 | 2015-04-10 |  | 44.5 | 0 | 2015-03-24 14:35 |  |  |  | 2015-03-23 | [19 empty] | 0
64165 | CDA | Audit |  | New | Minor Impact | Facilitation Audit Dated 24-Mar-2015 | Michael Arockiya Samy | Bestus Paul Daniel Franklin Inbaraj | 2015-03-25 21:04 |  |  | 2015-03-24 |  |  | 0 | 0 | 2015-03-24 11:12 | [23 empty] | 0
64157 | CDA | Bug |  | In Progress | Minor Impact | ANALYST-9258 (CLONE - Global Element Exception when trying to create a interface with xml file ) | Ramya Sakthivelu | Ramya Sakthivelu | 2015-03-24 11:03 |  | Release 6.0 | 2015-03-24 | 2015-03-25 | 16 | 12.5 | 20 | 2015-03-24 11:03 | [23 empty] | 0
64137 | CDA | Bug |  | Closed | High | ANALYST-9030; | Sharath Jaganathan | Sharath Jaganathan | 2015-03-25 10:39 |  | Release 6.0 | 2015-03-23 | 2015-03-27 | 6.5 | 6.5 | 50 | 2015-03-24 10:38 | 2015-03-25 10:39 |  | No clarification needed since it is work as designed | 2015-03-23 | 2015-03-24 | [10 empty] | No impact analysis is needed since the product is working as designed | No unit test is required since no code changes has been done | NO code changes are done and hence no code review required. | [5 empty] | 0
64135 | CDA | Bug |  | Closed | Minor Impact | Analyst-9260 | Prisla Sabatini Irudayaraj | Prisla Sabatini Irudayaraj | 2015-03-31 13:00 |  | Release 6.0 | 2015-03-23 | 2015-03-25 | 5.5 | 5.5 | 0 | 2015-03-24 10:31 | 2015-03-31 13:00 |  | no clarification | [12 empty] | no impact | Loaded the attached map and input. ran the java map test. No exception was thrown | no review comments | [5 empty] | 0
64072 | CDA | Bug |  | Closed | Minor Impact | CDA Stand-Up Meeting | Aishwarya Srinivasan | Aishwarya Srinivasan | 2015-03-26 15:23 |  | Release 6.0 | 2015-03-23 | 2015-04-30 | 0.65 | 0.65 | 0 | 2015-03-23 19:14 | 2015-03-26 15:23 | [22 empty] | 0
64069 | CDA | Bug |  | In Progress | Minor Impact | Working on the Contivo product | Aishwarya Srinivasan | Aishwarya Srinivasan | 2015-04-01 10:07 |  | Release 5.8.2 | 2015-03-23 | 2015-04-30 | 45.45 | 45.45 | 0 | 2015-03-23 19:08 | [23 empty] | 0
64068 | CDA | Bug |  | In Progress | Minor Impact | KT Session | Aishwarya Srinivasan | Aishwarya Srinivasan | 2015-03-31 18:59 |  | Release 5.8.2 | 2015-03-23 | 2015-04-30 | 4.1 | 4.1 | 0 | 2015-03-23 19:02 | [23 empty] | 0
64022 | CDA | Code Review |  | In Progress | Minor Impact | Code Review for Mar-2015 | Ramya Sakthivelu | Ramya Sakthivelu | 2015-03-24 11:01 |  | Release 6.0 | 2015-03-23 | 2015-03-31 | 16 | 1.5 | 0 | 2015-03-23 13:00 | [23 empty] | 0
63998 | CDA | Bug |  | In Progress | Minor Impact | ANALYST-9238; | Sharath Jaganathan | Sharath Jaganathan | 2015-04-01 11:08 |  | Release 5.8.2 | 2015-03-31 | 2015-04-02 | 16 | 16.65 | 70 | 2015-03-23 11:31 |  |  |  | 2015-03-20 | [19 empty] | 0
63936 | CDA | Bug |  | Closed | Minor Impact | ANALYST-9231 ("Output the mapping rule value only if the parent group exists" isn't working correctly) | Rushendra Babu Natarajan | Rushendra Babu Natarajan | 2015-03-31 12:55 |  | Release 6.0 | 2015-03-20 | 2015-03-27 | 6.5 | 6.5 | 100 | 2015-03-20 19:30 | 2015-03-31 12:55 |  | No need | 2015-03-20 | 2015-03-27 | [10 empty] | No Impact | Work as Designed | Work as Designed | [5 empty] | 0
63881 | CDA | Bug |  | Closed | Minor Impact | Issue 9245 | Phani Madhav Atchyutanna Jagan Rao | Phani Madhav Atchyutanna Jagan Rao | 2015-03-24 11:14 |  | Release 6.0 | 2015-03-18 | 2015-04-03 | 50 | 18.75 | 0 | 2015-03-20 12:52 | 2015-03-24 11:14 |  | Go To interface modeller and set the Recursion level to 1 and then save the map and run the map upgrade. | 2015-03-18 | [11 empty] | Not Applicable | Not Applicable | Not Applicable | Ticket moved to next sprint. |  |  |  |  | 0
63627 | CDA | Bug |  | Closed | Low | ANALYST-9263; | Sharath Jaganathan | Sharath Jaganathan | 2015-03-23 10:33 |  | Release 6.0 | 2015-03-18 | 2015-03-20 | 8 | 8 | 100 | 2015-03-19 11:26 | 2015-03-23 10:33 |  | No clarification needed | 2015-03-18 | 2015-03-20 | [10 empty] | Does not have an major impact since it is a gui related issue | tested with all possible use cases and ran the regression test cases after the fix | Reviewer:ramya reviewed the code and modified in such a way that added my if condition as a seperate method in Tmatrixtopsidecell.java and called that condition in the tmatrix.java too | [5 empty] | 0
63611 | CDA | Meetings |  | Closed | Minor Impact | Analyst - 9253 Discussion with bestus | Rushendra Babu Natarajan | Rushendra Babu Natarajan | 2015-03-19 10:57 |  | Release 6.0 | 2015-03-18 | 2015-03-18 | 1 | 1 | 100 | 2015-03-19 10:57 | 2015-03-19 10:57 |  |  | 2015-03-18 | [19 empty] | 0
63608 | CDA | Bug |  | In Progress | Minor Impact | ANALYST-9268 ("moveToChildGroup: commit failed while moving from group rateplan" when inserting into a database ) | Ramya Sakthivelu | Ramya Sakthivelu | 2015-03-24 11:01 |  | Release 6.0 | 2015-03-19 | 2015-03-24 | 16 | 11.5 | 0 | 2015-03-19 10:30 | [23 empty] | 0
63375 | CDA | Bug |  | Closed | Minor Impact | ANALYST-9226; | Sharath Jaganathan | Sharath Jaganathan | 2015-03-20 19:24 |  | Release 6.0 | 2015-03-17 | 2015-03-20 | 12.5 | 12.5 | 100 | 2015-03-18 11:05 | 2015-03-20 19:22 |  | ramya Asked to show the output mismatch error instead of the missing date time error in the detail pane | 2015-03-17 | 2015-03-20 | [10 empty] | The issue does not have an impact,but fine tuned the error. | tested with all possible use cases and ran the regression test cases for the fix | Reviewer:Ramya reviewed the code and then modified the output value in the error to the exact rule result value. | [5 empty] | 0
62993 | CDA | Bug |  | In Progress | High | ANALYST-9257 CLONE - Opening a map in Analyst newer than 5.3 causes a NumberFormatException | Ramya Sakthivelu | Ramya Sakthivelu | 2015-03-24 11:01 |  | Release 6.0 | 2015-03-17 | 2015-03-25 | 8 | 7.5 | 80 | 2015-03-17 10:57 |  |  |  | 2015-03-16 | [19 empty] | 0
62992 | CDA | Bug |  | In Progress | Minor Impact | Analyst-9252 | Prisla Sabatini Irudayaraj | Prisla Sabatini Irudayaraj | 2015-03-31 12:59 |  | Release 6.0 | 2015-03-16 | 2015-04-03 | 18 | 19.5 | 0 | 2015-03-17 10:57 |  |  | no clarification | [12 empty] | this would impact the presentation functionality | [7 empty] | 0
62991 | CDA | Bug |  | Closed | Minor Impact | Analyst-9266 | Prisla Sabatini Irudayaraj | Prisla Sabatini Irudayaraj | 2015-04-01 10:41 |  | Release 6.0 | 2015-03-16 | 2015-04-01 | 32.5 | 32.5 | 0 | 2015-03-17 10:56 | 2015-04-01 10:41 |  | the issue mentioned there were tags generated for the mandatory fields, but one tag was generated so asked for clarification about this to stephen | [12 empty] | this would impact the default value functionality, and generating of empty tags when looping association exist | loaded the attached map and input. Ran the java map test. opened the saved output. the hs-serviceph-element is written 900 times. | the was a change in the approach which was suggested and it was fixed. | [5 empty] | 0
62984 | CDA | Bug |  | In Progress | Minor Impact | ANALYST-9251; | Sharath Jaganathan | Sharath Jaganathan | 2015-04-01 11:08 |  | Release 5.8.2 | 2015-03-31 | 2015-04-02 | 10 | 12.8 | 60 | 2015-03-17 10:46 |  |  |  | 2015-03-16 | [19 empty] | 0
62949 | CDA | Bug |  | Suspended | Minor Impact | ANALYST-9253 (Cannot generate the Java transformation throws stack overflow exception) | Rushendra Babu Natarajan | Rushendra Babu Natarajan | 2015-03-24 20:10 |  | Release 6.0 | 2015-03-16 | 2015-03-20 | 19.5 | 19.5 | 100 | 2015-03-16 20:07 |  |  | NO need | 2015-03-16 | [11 empty] | Suspended | Suspended | Suspended | Assigned to onsite person |  |  |  |  | 0
62779 | CDA | Bug |  | Closed | Minor Impact | Executing the sanity testcases for repo & Prism | Rammiyajoya Allwin Roegers | Rammiyajoya Allwin Roegers | 2015-03-18 11:49 |  | Release 6.0 | 2015-03-16 | 2015-03-20 | 8 | 8 | 0 | 2015-03-16 13:29 | 2015-03-18 11:49 | [22 empty] | 0
62711 | CDA | Bug |  | Closed | Minor Impact | Leave | Ramya Sakthivelu | Ramya Sakthivelu | 2015-03-24 11:01 |  | Release 6.0 | 2015-03-13 | 2015-03-13 | 8 | 8 | 100 | 2015-03-16 11:01 | 2015-03-24 11:01 |  | N/A | [12 empty] | N/A | N/A | N/A | N/A |  |  |  |  | 0
62701 | CDA | Bug |  | Closed | High | Working on resolved issue | Sharath Jaganathan | Sharath Jaganathan | 2015-03-17 10:45 |  | Release 6.0 | 2015-03-13 | 2015-03-20 | 7.1 | 7.1 | 100 | 2015-03-16 10:38 | 2015-03-17 10:45 |  | NO clarification needed | 2015-03-13 | 2015-03-16 | [10 empty] | No impact analysis needed since it is a resolved issue | ran the regression and then tested with all test scenarios | no code changes has been done. | [5 empty] | 0
62644 | CDA | Bug |  | Closed | Minor Impact | Testing resolved issues | Rushendra Babu Natarajan | Rushendra Babu Natarajan | 2015-03-24 20:08 |  | Release 6.0 | 2015-03-13 | 2015-03-20 | 8.75 | 8.75 | 10 | 2015-03-13 19:56 | 2015-03-24 20:08 |  | No need | 2015-03-13 | 2015-03-20 | [10 empty] | Testing | Testing | Testing | Testing |  |  |  |  | 0
62528 | CDA | Bug |  | In Progress | Minor Impact | Issue-9264 | Phani Madhav Atchyutanna Jagan Rao | Phani Madhav Atchyutanna Jagan Rao | 2015-03-31 12:43 |  | Release 5.8.2 | 2015-03-13 | 2015-04-10 | 60 | 25.25 | 0 | 2015-03-13 12:57 |  |  |  | 2015-03-12 | [19 empty] | 0
62511 | CDA | Bug |  | Closed | Minor Impact | ANALYST-9063; | Sharath Jaganathan | Sharath Jaganathan | 2015-03-13 11:56 |  | Release 6.0 | 2015-03-13 | 2015-03-13 | 7 | 7 | 100 | 2015-03-13 11:56 | 2015-03-13 11:56 |  | asked not to show the looping control editor for the empty group | 2015-03-12 | 2015-03-13 | [10 empty] | No impact analysis is needed since it is a gui issue | tested with group which has mapping field as well as which does not have the mapping field and with an empty group | Reviewer:ramya reviewed and accepted the changes made in the code | [5 empty] | 0
62461 | CDA | Bug |  | In Progress | Minor Impact | ANALYST-9265 (Mapped value doesn't get outputted for Java transformation if the logic group has present) | Rushendra Babu Natarajan | Rushendra Babu Natarajan | 2015-03-31 12:57 |  | Release 5.8.2 | 2015-03-12 | 2015-04-03 | 8 | 7.25 | 30 | 2015-03-12 20:01 |  |  | No need | 2015-03-12 | [11 empty] | Might have no | [7 empty] | 0
62316 | CDA | Bug |  | Suspended | Minor Impact | Analyst-9012 | Sharath Jaganathan | Sharath Jaganathan | 2015-03-13 11:53 |  | Release 6.0 | 2015-03-11 | 2015-03-13 | 0.8 | 0.8 | 100 | 2015-03-12 11:14 |  |  | Suspended the issue | 2015-03-11 | 2015-03-13 | [10 empty] | Suspended the issue | Suspended the issue | NO code review is required | since the issue is will be fixed in the future prism.suspending this issue. |  |  |  |  | 0
62312 | CDA | Bug |  | Closed | Minor Impact | ANALYST-9259(Global function projects listed as object) | Sharath Jaganathan | Sharath Jaganathan | 2015-03-12 11:06 |  | Release 6.0 | 2015-03-11 | 2015-03-13 | 6 | 6 | 100 | 2015-03-12 11:06 | 2015-03-12 11:06 |  | NO clarification is needed. | 2015-03-11 | 2015-03-11 | [10 empty] | No impact analysis is needed since it is a gui issue | Tested with all possible test cases. | Reviewer:Ramya approved the changes made in the apiproject.java. | [5 empty] | 0
62309 | CDA | Bug |  | Closed | Minor Impact | PTO On 11-Mar-2015 | Ganesh Moorthy Palanisamy | Ganesh Moorthy Palanisamy | 2015-03-12 10:16 |  | Release 6.0 | 2015-03-11 | 2015-03-11 | 8 | 8 | 0 | 2015-03-12 10:14 | 2015-03-12 10:16 | [22 empty] | 0
61936 | CDA | DAA | DAA #61924: CDA- DAA Findings (Feb 2015 issues) | New | Minor Impact | Retro outcomes not evidenced in iNia. | Daniel Jawahar | Bestus Paul Daniel Franklin Inbaraj | 2015-03-11 17:25 |  |  | 2015-03-11 |  |  | 0 | 0 | 2015-03-11 17:24 | [23 empty] | 0
61931 | CDA | DAA | DAA #61924: CDA- DAA Findings (Feb 2015 issues) | New | Minor Impact | Unit test results and review comments were not evidenced. (#47089) | Daniel Jawahar | Bestus Paul Daniel Franklin Inbaraj | 2015-03-11 17:25 |  |  | 2015-03-11 |  |  | 0 | 0 | 2015-03-11 17:11 | [13 empty] | NC | [9 empty] | 0
61930 | CDA | DAA | DAA #61924: CDA- DAA Findings (Feb 2015 issues) | New | Minor Impact | Tracker Bug is used for support issues. (#57344) | Daniel Jawahar | Bestus Paul Daniel Franklin Inbaraj | 2015-03-11 17:25 |  |  | 2015-03-11 |  |  | 0 | 0 | 2015-03-11 17:09 | [13 empty] | NC | [9 empty] | 0
61928 | CDA | DAA | DAA #61924: CDA- DAA Findings (Feb 2015 issues) | New | Minor Impact | WSR not evidenced in iNia. | Daniel Jawahar | Bestus Paul Daniel Franklin Inbaraj | 2015-03-11 17:25 |  |  | 2015-03-11 |  |  | 0 | 0 | 2015-03-11 17:06 | [13 empty] | NC | [9 empty] | 0
61927 | CDA | DAA | DAA #61924: CDA- DAA Findings (Feb 2015 issues) | New | Minor Impact | Metrics are not evidenced in iNia. | Daniel Jawahar | Bestus Paul Daniel Franklin Inbaraj | 2015-03-11 17:25 |  |  | 2015-03-11 |  |  | 0 | 0 | 2015-03-11 17:06 | [13 empty] | NC | [9 empty] | 0
61926 | CDA | DAA | DAA #61924: CDA- DAA Findings (Feb 2015 issues) | New | Minor Impact | Due date over but still issues are not closed (#57366) | Daniel Jawahar | Bestus Paul Daniel Franklin Inbaraj | 2015-03-11 17:25 |  |  | 2015-03-11 |  |  | 0 | 0 | 2015-03-11 17:06 | [13 empty] | NC | [9 empty] | 0
61925 | CDA | DAA | DAA #61924: CDA- DAA Findings (Feb 2015 issues) | New | Minor Impact | Previous DAA findings is not been closed (#48038, #48039, #48041) | Daniel Jawahar | Bestus Paul Daniel Franklin Inbaraj | 2015-03-11 17:25 |  |  | 2015-03-11 |  |  | 0 | 0 | 2015-03-11 17:06 | [13 empty] | NC | [9 empty] | 0
61924 | CDA | DAA |  | New | Minor Impact | CDA- DAA Findings (Feb 2015 issues) | Daniel Jawahar | Bestus Paul Daniel Franklin Inbaraj | 2015-03-11 17:25 |  |  | 2015-03-11 |  |  | 0 | 0 | 2015-03-11 17:05 | [19 empty] | NA |  |  |  | 0
61887 | CDA | Bug |  | Closed | Minor Impact | Executing sanity testcases for Analyst | Rammiyajoya Allwin Roegers | Rammiyajoya Allwin Roegers | 2015-03-16 13:30 |  | Release 6.0 | 2015-03-11 | 2015-03-13 | 13 | 13 | 0 | 2015-03-11 12:18 | 2015-03-16 13:30 | [22 empty] | 0
61789 | CDA | Bug |  | Closed | Minor Impact | GTWO KT | Arivanantham Arivalagan | Arivanantham Arivalagan | 2015-03-23 14:47 |  |  | 2015-03-10 |  | 1 | 1 | 100 | 2015-03-10 19:25 | 2015-03-23 14:46 | [22 empty] | 0
61470 | CDA | Bug |  | Closed | Minor Impact | REPO-479 (Project path has to appear properly in "Access control for objects" page) | Rushendra Babu Natarajan | Rushendra Babu Natarajan | 2015-03-24 20:02 |  | Release 6.0 | 2015-03-06 | 2015-03-20 | 8.75 | 8.75 | 100 | 2015-03-09 11:51 | 2015-03-24 20:02 |  | No need | 2015-03-06 | 2015-03-20 | [10 empty] | Might have no | Tested by selecting the deep level projects | Reviewer : Ramya No changes | [5 empty] | 0
61469 | CDA | Bug |  | Closed | Minor Impact | ANALYST-9255 Fix interaction between Min Occurs and GRF for looping groups | Ramya Sakthivelu | Ramya Sakthivelu | 2015-03-31 12:42 |  | Release 6.0 | 2015-03-09 | 2015-03-30 | 16 | 19.5 | 100 | 2015-03-09 11:51 | 2015-03-31 12:42 |  | Issue seems to be working as expected asked this to Nick and confirmed | 2015-03-09 | 2015-03-30 | [11 empty] | No code changes | No code changes | [5 empty] | 0
61466 | CDA | Meetings |  | In Progress | Minor Impact | Womens day celebration-2015 | Ramya Sakthivelu | CDA | 2015-03-13 12:38 |  | Release 6.0 | 2015-03-06 | 2015-03-31 | 3 | 3 | 90 | 2015-03-09 11:46 | [23 empty] | 0
61349 | CDA | Bug |  | Closed | Minor Impact | PTO | Rammiyajoya Allwin Roegers | Rammiyajoya Allwin Roegers | 2015-03-06 14:32 |  | Release 6.0 | 2015-03-06 | 2015-03-06 | 16 | 16 | 0 | 2015-03-06 14:31 | 2015-03-06 14:32 | [22 empty] | 0
61314 | CDA | Bug |  | Closed | High | Analyst-9229 | Prisla Sabatini Irudayaraj | Prisla Sabatini Irudayaraj | 2015-03-31 12:59 |  | Release 6.0 | 2015-03-05 | 2015-03-31 | 28.25 | 28.25 | 0 | 2015-03-06 12:20 | 2015-03-31 12:59 |  | no clarification | [12 empty] | this will impact the map test and creating java transform. | [7 empty] | 0
61313 | CDA | Bug |  | Closed | Minor Impact | Analyst-9235 | Prisla Sabatini Irudayaraj | Prisla Sabatini Irudayaraj | 2015-03-31 12:51 |  | Release 6.0 | 2015-03-05 | 2015-03-31 | 23.5 | 23.5 | 0 | 2015-03-06 12:19 | 2015-03-31 12:51 |  | Tested the cases mentioned by stephen Case 2 and 3 are working as expected both 5.2 and 5.8. Case 1 : If the target group have the minOccurance of 1 and we have 3 occurances of inputs(1 with value others are empty), In this case currenlty we have 2 empty tags and 1 tag with value in the Output. Do we need to write only one tag with value since target group's minoccrs is 1 and empty tags should be removed? checked with stephen | [12 empty] | this would impact the output generation | [7 empty] | 0
61288 | CDA | Bug |  | Closed | Minor Impact | Working on Issue 9238 | Phani Madhav Atchyutanna Jagan Rao | Phani Madhav Atchyutanna Jagan Rao | 2015-03-24 11:13 |  | Release 6.0 | 2015-03-05 | 2015-03-27 | 30 | 32 | 0 | 2015-03-06 11:52 | 2015-03-24 11:13 |  | Not Applicable | 2015-03-05 | [12 empty] | Not Applicable | Not Applicable | Not Applicable |  |  |  |  | 0
61254 | CDA | Bug |  | Closed | Minor Impact | Analyst-9251 | Sharath Jaganathan | Sharath Jaganathan | 2015-03-12 11:12 |  | Release 6.0 | 2015-03-05 | 2015-03-13 | 21.2 | 21.2 | 100 | 2015-03-06 10:35 | 2015-03-12 11:12 |  | asked to fix in the interfacetype issue,that once it gets changed the transform option should be listing all possible transformation and also for the generated sample data | 2015-03-05 | 2015-03-11 | [10 empty] | NO impact analysis is needed | Testes by changing all the interface type | Reviewer:Ramya reviewed the code and then suggested to do the fix in the interfacetypepanel.java rather in the manager#setinterfacechange(). | [5 empty] | 0
60970 | CDA | Bug |  | Closed | Minor Impact | ANALYST-9256 (ConcurrentModificationException) | Rushendra Babu Natarajan | Rushendra Babu Natarajan | 2015-03-10 11:34 |  | Release 6.0 | 2015-03-04 | 2015-03-10 | 5 | 5 | 100 | 2015-03-05 10:57 | 2015-03-10 11:34 |  | No need | 2015-03-04 | 2015-03-05 | [10 empty] | Might Have no | Add some of the ffd's like filters variables and tested it | Reviewer : Ganesh No changes | [5 empty] | 0
60955 | CDA | Bug |  | Closed | Minor Impact | ANALYST-9256 | Ganesh Moorthy Palanisamy | Ganesh Moorthy Palanisamy | 2015-03-12 10:22 |  | CVMS Sprint 058 20150313 | 2015-03-04 | 2015-03-13 | 6.5 | 6.5 | 0 | 2015-03-05 09:57 | 2015-03-12 10:22 |  | Asked for Exact case but the walkthrough in code fixed issue | [13 empty] | NA | Checked with Ankit before committing the code.Added the direct implementation rather using ConcurrentHashMap | NA |  |  |  |  | 0
60770 | CDA | Bug |  | Closed | Minor Impact | Analyst-9248 | Ganesh Moorthy Palanisamy | Ganesh Moorthy Palanisamy | 2015-03-24 11:14 |  | Release 6.0 | 2015-03-02 | 2015-03-31 | 3.5 | 3.5 | 0 | 2015-03-04 12:26 | 2015-03-24 11:13 |  | Added the necessary clarification in JIRA | [13 empty] | No Code changes are done | NA | [5 empty] | 0
60769 | CDA | Meetings |  | Closed | Minor Impact | Sprint-58 Kick Off | Ganesh Moorthy Palanisamy | Ganesh Moorthy Palanisamy | 2015-03-05 10:00 |  | CVMS Sprint 058 20150313 | 2015-03-02 | 2015-03-02 | 0.5 | 0.33 | 0 | 2015-03-04 12:24 | 2015-03-05 10:00 | [22 empty] | 0
60768 | CDA | Bug |  | Closed | Minor Impact | PTO | Ganesh Moorthy Palanisamy | Ganesh Moorthy Palanisamy | 2015-03-04 12:28 |  | CVMS Sprint 058 20150313 | 2015-03-02 | 2015-03-02 | 4 | 4 | 0 | 2015-03-04 12:22 | 2015-03-04 12:23 | [22 empty] | 0
60767 | CDA | Bug |  | Closed | Minor Impact | PTO | Ganesh Moorthy Palanisamy | Ganesh Moorthy Palanisamy | 2015-03-04 12:27 |  | CVMS Sprint 058 20150313 | 2015-03-03 | 2015-03-03 | 8 | 8 | 0 | 2015-03-04 12:19 | 2015-03-04 12:21 | [22 empty] | 0
60736 | CDA | Bug |  | Closed | Minor Impact | ANALYST-9249 (We get a fatal error when a required source element is empty.) | Rushendra Babu Natarajan | Rushendra Babu Natarajan | 2015-03-09 11:47 |  | Release 6.0 | 2015-03-03 | 2015-03-06 | 10 | 10 | 100 | 2015-03-04 11:06 | 2015-03-09 11:47 |  | No need | 2015-03-03 | 2015-03-06 | [11 empty] | Tested by giving various types of values in the rule. | Reviewer : Ganesh No Changes | [5 empty] | 0
60733 | CDA | Training |  | Closed | Minor Impact | Creating Ang-js PPT for presentation | Rushendra Babu Natarajan | Rushendra Babu Natarajan | 2015-03-04 11:03 |  | Release 6.0 | 2015-03-03 | 2015-03-03 | 3 | 3 | 100 | 2015-03-04 11:03 | 2015-03-04 11:03 |  |  | 2015-03-03 | 2015-03-03 | [18 empty] | 0
60571 | CDA | Bug |  | In Progress | Minor Impact | Team support -MAR 2015 | Ramya Sakthivelu | Ramya Sakthivelu | 2015-03-03 13:05 |  | Release 6.0 | 2015-03-03 | 2015-03-31 | 10 | 32.25 | 0 | 2015-03-03 13:05 | [23 empty] | 0
60569 | CDA | Bug |  | Closed | Minor Impact | Working On Issue 9226 | Phani Madhav Atchyutanna Jagan Rao | Phani Madhav Atchyutanna Jagan Rao | 2015-03-10 11:36 |  | Release 6.0 | 2015-03-02 | 2015-03-06 | 20 | 12 | 0 | 2015-03-03 13:05 | 2015-03-10 11:36 | [14 empty] | The issue arises when the call is made to getCurrentTime with the format. | NO Unit test failures. Unit tests are done by passing the format to getCurrentTime and also by not passsing the format to getCurrentTime. Other tests are also done by writing the rules to output the getCurrentDate | Code Review Is done and there are no comments | [5 empty] | 0
60567 | CDA | Bug |  | Closed | Minor Impact | Discussion with Bestus | Arivanantham Arivalagan | Arivanantham Arivalagan | 2015-03-03 13:03 |  |  | 2015-03-03 | 2015-03-03 | 0.75 | 0.75 | 100 | 2015-03-03 13:03 | 2015-03-03 13:03 | [22 empty] | 0
60565 | CDA | Bug |  | Closed | Minor Impact | ANALYST-9233 ( Map Testing GUI does not show all iterations when "Execute using 3.11..." is selected) | Ramya Sakthivelu | Ramya Sakthivelu | 2015-03-10 11:26 |  | Release 6.0 | 2015-03-02 | 2015-03-06 | 24 | 29 | 30 | 2015-03-03 13:02 | 2015-03-10 11:26 |  | No clarification | [13 empty] | Ran all the java standalone regression | Code review has been done by Bestus, no review comments | [5 empty] | 0
60546 | CDA | Bug |  | Closed | High | Analyst-9204 | Prisla Sabatini Irudayaraj | Prisla Sabatini Irudayaraj | 2015-03-03 12:54 |  | Release 6.0 | 2015-03-02 | 2015-03-04 | 4 | 4 | 100 | 2015-03-03 12:45 | 2015-03-03 12:53 | [14 empty] | no Impact since the issue is not reproduced | Scenario 1: Loaded the attached map loaded the input there was no exception and the java transform was successful. Scenario 2: Changed the class-path and gave some invalid values. loaded the map and the input no exceptions was available. Scenario 3: Also changed the key files for various combinations tried t load the map and the input no exceptions | no review was done since the issue is not reproduced | [5 empty] | 0
60545 | CDA | Bug |  | Closed | High | Analyst-9232 | Prisla Sabatini Irudayaraj | Prisla Sabatini Irudayaraj | 2015-03-05 11:34 |  | Release 6.0 | 2015-03-02 | 2015-03-05 | 11.75 | 11.75 | 100 | 2015-03-03 12:45 | 2015-03-05 11:34 |  | we had some clarification about the occurrence of the fatal error scenarios checked with client and removed the fatal error | [12 empty] | no impact | Loaded the attached map Load the input and run the java map test. No error was thrown. If the GRF was false then the value was not outputted | no review comments | [5 empty] | 0
60508 | CDA | Bug |  | In Progress | Minor Impact | Test case failures | Rushendra Babu Natarajan | Rushendra Babu Natarajan | 2015-03-31 12:58 |  | Release 5.8.2 | 2015-03-02 | 2015-04-03 | 25 | 57.5 | 20 | 2015-03-03 11:34 |  |  | No Need | 2015-03-02 | [11 empty] | No Impact, Test case failures. | [7 empty] | 0
60493 | CDA | Bug |  | Closed | Minor Impact | ANALYST-9248 (Analyst does not complain at compile time when a group rule field is populated with a non-boolean) | Rushendra Babu Natarajan | Rushendra Babu Natarajan | 2015-03-16 20:00 |  | Release 6.0 | 2015-03-02 | 2015-03-13 | 5 | 5 | 100 | 2015-03-03 11:15 | 2015-03-16 20:00 |  | No need | 2015-03-02 | 2015-03-13 | [10 empty] | Might hav no | Tested by giving complex rules | Reviewer : Ramya No changes | [5 empty] | 0
60477 | CDA | Action |  | Closed | Low | PTO | Sharath Jaganathan | Sharath Jaganathan | 2015-03-03 10:06 |  | Release 6.0 | 2015-03-02 | 2015-03-03 | 8 | 8 | 100 | 2015-03-03 10:06 | 2015-03-03 10:06 | [22 empty] | 0
60272 | CDA | Support |  | Closed | Minor Impact | Analysis on Git working with eclipse EGIT and also modifying user name and committing it | Ganesh Moorthy Palanisamy | Ganesh Moorthy Palanisamy | 2015-03-02 16:34 |  | CVMS Sprint 053 20150102 | 2015-02-27 | 2015-02-27 | 6 | 6 | 0 | 2015-03-02 16:33 | 2015-03-02 16:34 | [22 empty] | 0
60235 | CDA | Meetings |  | In Progress | Minor Impact | Standup meeting - -MAR / 2015 | Ramya Sakthivelu | CDA | 2015-03-31 18:59 |  | Release 5.8.2 | 2015-03-02 | 2015-03-31 | 38.13 | 38.88 | 0 | 2015-03-02 13:14 |  |  |  | 2015-03-02 | [19 empty] | 0
60227 | CDA | Meetings |  | Resolved | Minor Impact | Working with Bestus & sharath for ANALYST-8237 | Ramya Sakthivelu | Ramya Sakthivelu | 2015-03-02 12:54 |  | Release 6.0 | 2015-02-27 | 2015-02-27 | 1.5 | 1.5 | 100 | 2015-03-02 12:54 | [23 empty] | 0